## Sheet1
| committee_name | committee_code | file_name | title | govtrack | speaker | speech
0 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. The subcommittee will come to order to receive testimony concerning the F-35 Joint Strike Fighter, the JSF, program. I want to welcome our panel of distinguished witnesses, Dr. Michael Gilmore, Director of Operational Test and Evaluation [OT&E]; Dr. Michael J. Sullivan, Director of Acquisition and Sourcing, Government Accountability Office [GAO], and a good southwest Ohioan; the Honorable Sean Stackley, Assistant Secretary of the Navy for Research, Development, and Acquisition; and Lieutenant General Christopher C. Bogdan, F-35 Program Executive Officer. Because we were held up for votes, I am going to enter my statement for the record, if there is no objection. [The prepared statement of Mr. Turner can be found in the Appendix on page 31.]
1 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. And we will also enter Ms. Sanchez's statement in for the record, and we will proceed right to the statements of our witnesses. [The prepared statement of Ms. Sanchez can be found in the Appendix on page 33.]
2 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. I believe we will start with Dr. Gilmore.
3 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. Thank you, Mr. Chairman, members of the committee. In my opening statement I will focus on readiness for operational test and evaluation. My estimate is the program won't be ready to begin IOT&E [initial operational test and evaluation] until mid-calendar year 2018 at the earliest. That would be about a 1-year delay relative to what the program is carrying currently as its objective dates and about 6 months relative to its threshold dates. The reasons are the following. The most complex mission system testing remains, as does verification and fixes to significant problems, some of those fixes already having been identified and some not. Mission system stability, including the radar, still a problem. Inadequate fusion of sensor information from sensors on the same aircraft, as well as among different aircraft, continues to be a problem. There are shortfalls in electronic warfare, electronic attack, shortfalls in the performance of the Distributed Aperture System, and other issues that are classified with regard to mission systems. Stealth aircraft are not invisible. To achieve success against the modern stressing mobile threats we are relying on our $400 billion investment in F-35 to provide, mission systems must work, in some reasonable sense of that word. And we must provide every incentive to the contractors to make the mission systems work leading up to and after IOT&E, in my view. The program has now changed its approach from schedule-driven software releases, which had overlaid old problems on top of new problems, to a capabilities-based approach. So now the program is addressing the significant deficiencies with a given version of software prior to proceeding with the next version, and I certainly commend that approach. And that should help work through and solve some of these problems that I have mentioned with mission systems. Other reasons IOT&E is likely to be delayed include the need for weapons testing and certification. The rate at which that has been done in the past must triple in order to get all the events done. There has been talk of cutting the number of events by two-thirds. If that occurs, that would simply shift the work to IOT&E and make essentially certain late discoveries of problems requiring fixes during IOT&E. The program is exploring ways to up the rate of testing, including using ranges at Eglin, and that would be a good decision, but decisions and action need to be taken soon. There is also the issue of certification of full weapons usage throughout the full flight envelope. The most recent test community estimates are that that would occur in October 2017 for F-35A, February 2018 for F-35C, and May 2018 for F-35B. And we are looking at this. Some have proposed an incremental rolling start to occupational tests. That may not be practical, and it was certainly problematic when we tried it on F-22. There are still problems with the Autonomics Logistics Information System [ALIS], which is critical to the combat operations of the aircraft. There are many resource-intensive workarounds still required. Under the program's current schedule, ALIS 3.0, the full capability version required for IOT&E, would not be released until the first quarter of 2018. There is also the need for concurrency-driven extensive modifications required to early-lot aircraft bought for IOT&E when it was thought that IOT&E would begin in 2013. The current unmitigated--meaning no measures taken to correct the problem--schedule shows mods extending into third quarter calendar year 2019. The program is, however, working on a multipronged approach, including using later-production aircraft slated for operational use and taking hardware from recently delivered aircraft on the production line that could move the completion of those modifications into 2018, and a decision is needed now on that. There are also inadequacies in the U.S. Reprogramming Lab that is used to generate the Mission Data Files, which are essential to the success in combat and certainly success in operational testing of the aircraft. The program's optimistic schedule for delivery of a validated--but, in my view, very possibly inadequate--Mission Data File for operational testing is the third quarter of 2017, but that date assumes the U.S. Reprogramming Lab receives a fully capable version of Block 3F by April 2016, next month, which we already know under the program's current plans will not happen until this summer at the soonest. So for all these reasons, I suspect that we won't be ready for operational testing until mid-calendar year 2018. Thank you. [The prepared statement of Dr. Gilmore can be found in the Appendix on page 35.]
4 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Mr. Sullivan.
5 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. Good morning, Mr. Chairman, members of the subcommittee. It is a pleasure to be here to discuss the progress on the F-35 program today. I have a written statement that I will submit for the record, and I just want to summarize five of the major points in that statement in my oral remarks. First, the Department [of Defense] is now planning to add new capability, known as Block 4, to the F-35 beyond its baseline capability and is planning to manage that effort as part of the existing program, rather than establishing a separate business case and baseline for this new work. This has significant implications as far as the Congress' role in oversight. This modernization effort is like a new program with estimated cost of about $3 billion over the next 6 years. That price tag alone would qualify it as a major defense acquisition program in its own right, and it should be managed as such, so that it is subject to the same statutory and regulatory reporting as any other program its size. The F-22 provides precedent for this. It began its modernization effort as part of the existing baseline program and it eventually established a separate business case and developed into a major acquisition program with its own Milestone B in order to better track progress and cost changes. Second, although the program has been managing costs very well since 2010, the Nunn-McCurdy breach back then, and cost estimates have actually decreased since then, it still poses significant affordability challenges for the Department and the Congress. As production begins to increase and the program begins procuring more aircraft each year, the Department is expected to spend about $14 billion per year over the next decade and will average about $13 billion per year over the next 22 years until all planned purchases are complete in 2038. These annual funding challenges will compound as the program begins to stack its funding needs against other large acquisitions, such as the bomber program, the tanker program that is ongoing, the Ohio-class submarine replacement, the new carrier, and many other very large programs. It is important to note this is just the remaining acquisition cost for the F-35. As we all know, the cost to operate and maintain the F-35 across its entire life cycle is estimated now at about $1 trillion, which has added to that overall price tag. My third point is software development and developmental flight testing of the F-35 are now nearing completion, but the program faces challenges in getting all of its development activity completed on time. I think Dr. Gilmore covered that pretty well. It is through with 80 percent of its developmental flight tests. It has completed the first three blocks of software, and it is now working to close out flight testing of its final block of software, Block 3F. That is the critical block of software as it will provide the full warfighting capabilities required for the F-35. Program officials have stated that there would be as much as a 3-month delay. We have done our own analysis and we think it could be more in line with 6 months. And I think Dr. Gilmore's analysis indicates even longer than that. Fourth, with regard to technical risks on the program, the program has most recently found fixes for its engine seal problem that we were talking about last year and the design of the helmet mounted display. And it has begun to retrofit aircraft with those fixes. They are not all in, but the solutions are there. Two new challenges have recently been identified. One concerns the ejection seat and the other concerns the wing structure of the carrier variant. The program is working now to find solutions to each of those problems. I think on the ejection seat they have a pretty good concept figured out to solve that one. It should also be noted that the Autonomic Logistics Information System, known as ALIS, continues to be challenging and has been cited as one of the most significant outstanding risks to the program today, and that has a lot to do with operations and maintenance, as you know. Finally, manufacturing and production data continue to show a positive trend toward more efficient production. The amount of labor hours it is taking to build each aircraft continues to go down, quality is increasing, and engineering changes have been reduced significantly. While there are still issues with late parts, this is consistently improving as well. Contractors are now delivering aircraft on time or ahead of schedule. We continue to track the measures for the aircraft's reliability and maintainability. And while they still fall short of expectations, they continue to improve, and there is still time to achieve the program's required goals at the right time. I will close with that. I look forward to your questions. [The prepared statement of Mr. Sullivan can be found in the Appendix on page 67.]
6 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. General Bogdan. General Bogdan. Thank you, Mr. Chairman. Chairman Turner, distinguished members of the committee, thank you for the opportunity to address the committee regarding the F-35 program. My purpose here today is to provide you a balanced assessment of where the program stands. That means I will tell you the good, the bad, and the ugly about the program, and tell you what my team is doing to reduce costs on the program and improve the F-35's performance and meet our scheduled commitment. Overall, the F-35 program is executing fairly well across the entire spectrum of acquisition, to include development and design, flight test, production, fielding, base stand-up, maintenance and support, and building a global sustainment enterprise. The program is at a pivot point and is now rapidly changing, growing, and accelerating. We will be finishing our 15-year development program in late 2017 and beginning to transition to a leaner, more efficient follow-on modernization program. We will see production grow from delivering 45 aircraft in 2015 to delivering over 100 aircraft in 2018 and up to 145 aircraft by 2020. Additionally, in the next 4 years we will continue to stand up 17 new operating bases all over the world. We are also accelerating the creation of our heavy maintenance and repair capabilities, and supply chain, throughout the globe, including the Pacific, European, and North American regions. However, the program is not without risks and challenges, as these come with any program of this size and complexity. I am confident that the current risks and issues we face can be resolved and we will be able to overcome future problems and deliver the full capability that we have committed to. I have often said that the mark of a good program is not that it has no problems, but rather that it discovers problems, implements solutions, improves the weapon system, and at the same time keeps the program on track. I believe we have been doing that for a number of years now. Let me highlight a few of our recent accomplishments since our last hearing. Last year, we began U.S. Air Force and partner pilot training at Luke Air Force Base, where a blend of U.S. and partner F-35 instructor pilots are helping train U.S. and other partner pilots. The Air Force is now receiving F-35As at Hill Air Force Base in Utah and training is underway to ready its first combat-coded squadron to be operational this year. Also, the United States Marine Corps successfully flying and deploying to austere sites for training, dropping and shooting live weapons with its F-35Bs. In addition, industry is committed to and then successfully delivered 45 airplanes last year, including the first aircraft that was produced in Italy and assembled in their factory in Cameri. From a production perspective, we have delivered a total of 172 aircraft to our test, operational, and training sites. On the cost front, the price of purchasing an F-35 continues to decline steadily, lot over lot. This is a trend I believe will continue for many years. I expect the cost of an F-35 with an engine and fee to decrease from about $108 million this year to about $85 million in 2019. As I said before, the program is changing, growing, and accelerating, but it is not without issues, risks, and challenges. So let me highlight a few of those areas. On the technical front we have a number of risks. At the top of my list are both software and our maintenance system, known as ALIS. On the software front we have seen stability issues recently with our Block 3 software and we are currently in the process of fixing and flight testing those fixes. We have also experienced issues with the development of our next version of ALIS, known as ALIS 2.0.2, and I am prepared to discuss these issues with you, as well as other risks and issues, such as our egress system, aircraft modifications, and our Reprogramming Labs. I am also prepared to discuss Air Force IOC [initial operating capability], initial operational testing, recent U.S. Air Force and Marine Corps deployments, and the status of our partners and FMS [foreign military sales] customers. In summary, the program is moving forward, sometimes slower than I would like, but moving forward and making progress nonetheless. We are nearing the completion of development and flight test in late 2017. We are ramping up production, standing up new bases, growing the global sustainment enterprise, and continuing to drive cost out of the program. I intend to continue leading this program with integrity, discipline, transparency, and accountability. It is my intention to complete this program within the resources and the time I have been given, and I intend on holding my team and myself accountable for the outcomes on this program. Thank you again for the opportunity to discuss the program. I look forward to your questions. [The joint prepared statement of General Bogdan and Secretary Stackley can be found in the Appendix on page 87.]
7 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you. Mr. Stackley.
8 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Secretary Stackley. Chairman Turner, distinguished members of the subcommittee, thank you for the opportunity to appear before you today to testify on the F-35 Joint Strike Fighter program. I will provide brief opening remarks and submit a formal statement for the record. One year ago, we discussed with the subcommittee the challenges facing the program at that time and our plans to address those challenges. In the course of this past year cost, schedule, and technical performance of the Joint Strike Fighter have steadily improved across each variant of the aircraft, in each phase of the program, development, production, and sustainment. Known technical issues are being driven to closure and the aircraft's capabilities, measured in terms of flight envelope, mission systems, and weapons delivery, are being steadily expanded in support of each service's requirements for initial operating capability, or IOC. As noted, production of F-35 aircraft and engines has improved from lot to lot in terms of unit cost, schedule performance, improved quality, reduced rework, and concurrency related costs. These positive trends are being sustained while also methodically increasing our rate of production. The pacing activity on the program today is flight testing, which itself is being paced by the incremental release of warfighting capability and mission system software blocks, commonly referred to as Block 2B, 3i, and 3F. Block 2B testing completed in 2015 and provided the capability required to support the Marine Corps' declaration of IOC in July 2015. The completion of Block 3i testing has been delayed pending correction of software stability issues. In the course of the next week, we commence flight testing what is planned to be the final build of Block 3i capability, designed to improve that stability, all in support of the Air Force IOC scheduled later this year. Completion of the final block, Block 3F, poses the greatest remaining challenge to completion of system development. Block 3F includes the more complex functionality of the three software baselines, including what is referred to as sensor fusion. Further coding and testing of Block 3F has been impacted by resource demands, software engineers, and lab facilities associated with supporting completion of earlier software builds. These factors add up to the program's estimate of 4 months schedule risk to completion of Block 3F developmental testing. This projection still supports the Navy IOC with Block 3F in 2018. That said, we are wary that further technical issues are certain to emerge as we press on with testing, and it will be critical that the program rapidly correct these deficiencies while mitigating their impact on both test and production. The program's commitment is to mitigate these risks going forward and to do so within the bounds of the program's budget while delivering the full capability defined by the Lightning II requirements document. Meanwhile, the program's focus is increasingly shifting to operations in support of in-service aircraft. The program has accumulated 50,000 flight hours, and with 152 aircraft operating at 8 bases across the country, the warfighter's experience and feedback on the aircraft and support systems is beginning to shape the program's priorities. The Marines have two full squadrons in operation today and will stand up their third this June. They are building momentum as the service and the vanguard of the F-35 effort, gaining capability and confidence and employing it tactically every day. They have demonstrated operations from an austere forward operating base at Twentynine Palms in support of the Marine Corps combined arms exercise. They are training British pilots, as well as first tour Marine Corps pilots, in Beaufort, South Carolina. They will deploy the Nation's first operational F-35 squadron less than a year from now to Marine Corps Air Station Iwakuni, Japan, in January 2017. Marine pilots love this plane and the capability it brings to the Marine Corps air-ground task force. Meanwhile, delivery of Air Force F-35A aircraft at Eglin Air Force Base are completed, training for Air Force international partner pilots at Luke Air Force Base continues to ramp up, and the Air Force first operational squadron is filling out at Hill Air Force Base with seven aircraft at Hill and remaining aircraft completing modifications to support IOC. Separately, the Navy has gained extensive experience demonstrating launch, recovery, handling, and support of the F-35C during at-sea trial periods aboard the aircraft carriers Eisenhower and Nimitz and a third sea trial scheduled for later this year. Two key points regarding operations and sustainment require mention. First, with particular regard to aircraft reliability, maintainability, and availability, or RM&A, one year ago we reported that overall performance in this area was poor and trending poor. Concerted efforts by the government/industry team have reversed those trends. And while we have much work remaining, improvements to design, parts availability, maintenance training and support, and tooling are yielding improved performance in the key metrics. RM&A will remain a principal focus area for the program in the years ahead. Second, the program is working closely with the services, our international partners, and industry to formulate an operating and support strategy for the program including the business plan that will accompany this strategy and an overarching O&S [operations and support] war on cost. A critical element of the O&S plan is the Autonomic Logistic Information System, or ALIS. ALIS continues to mature, improving with each version fielded. In the near term, we will be testing a new version, ALIS 2.0.2, which we expect to support the Air Force IOC. Additionally, to improve turnaround time for fixing issues highlighted by fleet maintainers, we have commenced delivery of service packs aimed to be more timely and responsive to a warfighter's immediate needs. In the long term, however, ALIS has yet to meet its full promise, and we will need to go the full distance in that regard if we are going to succeed in meeting our goals for reducing the ownership cost and increasing the operational availability for this complex aircraft, and we are committed to that end. In summary, the F-35 program is making solid progress across the full spectrum of development, production, testing, and fielding of capability. As known issues are retired, new issues will emerge, and these too will be wrestled to closure. The program's forecast for delivery of initial operating capability for each of the services, including risk, is largely unchanged from one year ago. Yet, the size and complexity of this program and the capability it represents is such that a great amount of work remains ahead, leading to each ensuing IOC and subsequent operations and sustainment and modernization of the aircraft. We are careful to neither minimize our assessment of the inherent risks nor to avoid them, but rather to assess them realistically and manage them aggressively. The warfighter and our international partners deserve nothing less. Mr. Chairman, again, thank you for the opportunity to testify today on the Joint Strike Fighter program. I look forward to answering your questions. [The joint prepared statement of Secretary Stackley and General Bogdan can be found in the Appendix on page 87.]
9 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you, gentlemen. I want to start with a question that goes to the public's perception of this plane, the F-35. We all are very much aware of the difficulties that the F-35 has had both in development and in production and certainly in getting to operational capability. But I was surprised the other morning to wake up in my own hometown--Mr. Sullivan, you hail from Wright-Patterson Air Force Base, so you may have similarly seen a huge headline across the Dayton Daily News that says: ``Ohio Voters Favor Canceling Jet Fighter.'' I thought it was kind of interesting for a couple of reasons. One, no one called me to ask me to quote for it, and it is my local newspaper. But it's a Washington bureau that quotes a University of Maryland study, that then quotes a response from a Washington think tank. So I want to give you guys who actually know about the F-35 an opportunity to discuss what this article raises, because there is a fundamental flaw in the study that gives the screaming headline of Ohio voters favor canceling the jet fighter. Apparently, they did an online poll, and we all know the liability of online polls of course, but there are 520 registered voters in Ohio. And it concludes that Ohio voters favor upgrading current fighters instead of going forward with the F-35 and resulting in a $97 billion savings to taxpayers by 2037. Now, obviously, we have not done a very good job of communicating the importance of the F-35 and its capability and why it is necessary. But the article does, I do want to give Jack Torry, the author of the story, credit. He does end with Loren Thompson, chief executive officer of the Lexington Institute in suburban Washington, with this quote: ``It is impossible to upgrade any of our Cold War fighters that would be as survivable as a stealth plane. That is the biggest single appeal of the F-35, is that most enemy radars simply can't see it. You can't shoot down what you can't see.'' So the article concludes with an interesting point. But the fact that a poll is taken asking people would they rather upgrade something that is not upgradable rather than proceed with the F-35 probably is something that bears our discussion. General Bogdan, help us here so we can give people some information so they can feel the importance of the investment in the F-35. General Bogdan. Yes, sir. I have to be a little bit careful because----
10 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. I want to recognize--let me say it for you--I want to recognize that a portion obviously of the F-35 capabilities go into the classified realm and its adversaries' capabilities are in the classified realm. So some of the capabilities of the F-35, the need for the F-35 cannot be discussed. But certainly the concept that this is fifth generation and that we cannot merely just plug and play with our old generation is probably worthy of a discussion. General Bogdan. Yes, sir. I agree with you. I have never been associated with a program in my 25-plus years of acquisition where the public perception and the reality are so different. Part of that is our problem for not telling the story, but part of it is because the program is so big that every minor issue becomes a big issue. We have had a past that has not been conducive to people believing in what we say. We have added years and billions of dollars to the program in the past. Even though that hasn't happened since 2010, people remember that. And it sometimes is difficult to explain to the public how air warfare is changing and how it is not a turn-and-burn airplane that looks really cool at an air show that is going to win the fight for the United States when we go into combat in the next 20 or 30 years. So we do have a perception problem and we do have an information gap there. What do we do about that? First and foremost, I do want to thank the Congress for helping us. You do. And you do that in a number of ways. One, you help us by holding us accountable. And when people know that you are holding us accountable and we base what we do and say on our results, then people will start having a better understanding and a better trust in what this weapon system can do. On the Department side--and this is where I have to be careful, because I shouldn't be necessarily a salesman for the F-35, you need me to be a little more balanced than that--but for our warfighters there is clearly a role for them to play in advocating for this airplane. And in the past we haven't done a great job of that, simply because the airplane was immature, we were only operating at a number of locations, and we are still developing it. So let me just give you a few things that are going to happen this year that might change that a little bit. The Air Force has stood up an F-35 heritage flight, which means that the F-35 is now going to be publicly displayed in many, many places over the next year. In fact, they have 14 public events between now and the end of 2016, some of the places including Luke Air Force Base, Langley Air Force Base, Fort Lauderdale, New York City, Chicago, Baltimore, Reno, Las Vegas. So the Air Force is getting out there with the airplane to these air shows and is going to start talking to folks about the airplane. The U.S. Marine Corps and the Navy, similarly, when they go to sea this year for their sea trials, will bring media with them so that they can tell their story. The Dutch, who are a partner on this program, are planning on bringing their two airplanes to the Netherlands in June for 2 weeks for the very thing that you just talked about, Congressman Turner, to introduce the airplane to their public, to talk about it, and to talk about why the airplane is needed for them. The U.S. Marines, the U.S. Air Force, and the U.K. will bring five airplanes to Farnborough and RIAT [Royal International Air Tattoo] this year in July at the U.K. Air Show. So I think getting out there and telling the story is part of what we need to continue to do. I also think we need to continue to base things on fact. And when people out there don't have the facts, then it is my job and my team's job to correct the record for that.
11 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. And, General Bogdan, in getting to the issue of facts, this poll asked people would they rather upgrade the current fighters instead of proceeding with the F-35. Loren Thompson said: It is impossible to do what they have asked, you cannot upgrade our Cold War fighters. Would you agree with the statement of Thompson and would you want to elaborate? General Bogdan. Yes, sir. You can only do so much with our fourth-generation fighters today. You can only add so many upgrades and structurally improve them to last a certain period of time. But what I will tell you from the knowledge I have on this program and the capabilities of the F-35, our legacy airplanes, now and in the future, will not survive the threat environments we know we are going to have to face. So no matter how much you upgrade them and how much you put into them, eventually they will not survive. This airplane differently. It will survive----
12 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. In combat. General Bogdan. In combat will survive for decades to come.
13 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. I just want to point one thing before I ask Mr. Sullivan his comments on this. This poll asks people about sticking with our current fighters through 2037. I wonder what the poll would have been if they asked people would they be willing to drive their current car through 2037. Mr. Sullivan, would you agree also that the poll is skewed in it gives people a false option, you can't upgrade our current fighters, as Loren Thompson says, in any way that would be as survivable as the F-35?
14 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. I think it is clear that this aircraft, fifth-gen aircraft, does things that the generations in the past can't do, won't ever be able to do. The stealthiness alone is a major part of this, but it is also probably more versatile. It is three different variants. It is replacing or complementing a number of different aircraft that are growing older every day as we sit here and are having service life extensions and things like that. So, yeah, I would agree that the F-35 is going to be a more versatile and a more powerful threat than what we have existing. And I think probably a lot of this has just come from--the past is the past, I understand that, but people still see a lot of money being put forth for the F-35. The other thing, I think, that you have to consider is that some of these aircraft, their production lines are shut down or they are not as hot as they used to be. And you can't, I think, as General Bogdan said, you can't plug and play these new technologies into those old aircraft anyway. So, yeah.
15 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Mr. Sullivan, I appreciate your comments on that because you being the Director of Acquisition and Sourcing for this program with the U.S. Government Accountability Office, you are responsible for giving us some of the most critical oversight information that we have on the program. I know you know its difficulties and the areas in which we struggle to try to make certain that the program is effective. So I appreciate your overarching statement.
16 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. Our beef has always just been with the acquisition strategy of this and many other programs. It takes way longer and costs more than they thought. But we have never really challenged the need for this or what its capabilities are eventually going to bring us.
17 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Excellent. Mr. Stackley, Dr. Gilmore, do you wish to comment on this? Excellent.
18 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. The fourth-generation aircraft that we have and the systems that they have, and even with upgrades, wouldn't be able to handle the threats that we have already seen being deployed by our potential enemies for over half a decade. Those are very challenging air defense threats that are mobile, so you can't count on knowing where they are. The F-35, with mission systems that work as I alluded to in my opening statement, will provide capability that we don't have in any other platform to dynamically sense that very stressing mobile threat environment you can't know ahead of time with certainty and deal with it. So that is why it is so important that we get the F-35, including its mission systems, to work. It will provide us capability that we otherwise won't have and can't get in upgraded systems.
19 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Mr. Stackley.
20 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Secretary Stackley. Sir, let me just add, our operational planning for major combat operations, first and foremost, relies upon air superiority, air dominance. The F-35 is not being designed and built for the fight today, it is being designed and built for the fight in the future against the high-end threat. So we are not willing to take risk in terms of maintaining air superiority that we will need in the 2020s, 2030s, and beyond. And the capabilities that are being brought to this aircraft are what we envision today as that necessary to overcome the threat in the future. I agree with Loren Thompson here that somebody is offering a false choice when they say we can just upgrade the existing fighters to get that level of capability. You cannot. The Navy/Marine Corps does have a mixed fleet in the future of fourth- and fifth-generation aircraft. We will continue to have a mixed fleet at least through the mid-2030s. But we cannot enter high-end fight without the fifth-generation capability that the JSF brings. That is why we are so committed to this capability.
21 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you. Very important discussion. Now turning, however, to some of the issues and difficulties that we have in making certain that this plane reaches its full potential. General Bogdan, Dr. Gilmore, and Mr. Sullivan's testimony indicate that significant challenges still do remain in completing the final software block, Block 3F. As you know, this is the version of software that gives the F-35 a full wartime capability, so it is very important. You also indicated in your testimony that Block 3F software is likely to be delivered 4 months late. What is the operational significance if this software is delivered 4 months late? Could it impact the current scheduled initial operational test and evaluation, IOT&E test? And what risk-mitigation actions are you taking to be able to fix this? General Bogdan. Thank you, sir. The issue today with the Block 3 software--and we see the problem in both our 3i, or 3 initial, software and in our 3F software--has to do with stability. And just very quickly, what the pilots are seeing is, when they take off and they need to use the sensors, particularly the radar, there are some instances where the communication between the radar and the main computers in the airplane are mistimed. And that mistiming builds up little delays. And eventually those delays get to be big enough where the radar shuts off. Okay? And the radar will recover, but it will recover and take a few minutes to regain the picture that it had. Some of the other sensors experience the same thing. That is not good. We are experiencing that kind of problem about once every 4 hours of flight time. We need the system to be much more stable in that, something on the order of once every 8 to 10 hours. So what we did when we found this problem out in the last few months is we went back and did a root cause analysis. As I just talked about, we know it is a timing issue. Lockheed Martin has a number of fixes in the software that we are about to flight test, starting next week in our next version of 3i software. In the next month or so we will know if those fixes work. If those fixes work, the stability fixes and some of the other software fixes, then the impact of this problem to Air Force IOC will be minimal. The impact to the remaining testing of 3F, as I said, will probably just delay the end of flight test about 4 months. That does not impact Navy IOC because we had some margin there, but it clearly would impact how ready the airplanes are for IOT&E. So we are looking forward to the flight tests that we are going to do in the next month or so to see if we have this solved. If we do have it solved, again, no impact to Air Force IOC, no impact to Navy IOC, but probably an impact overall to the end of testing, and that would eventually impact the start of IOT&E.
22 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Mr. Bogdan, I must have misunderstood. You were describing a problem with the software that you said would occur one time every 4 hours, but it would be okay if it occurred every 8 to 10 hours. Isn't that still a problem with the software? General Bogdan. With 8 million lines of code in the airplane, it is not unusual for both legacy airplanes and modern fifth-generation airplanes every now and then to have to reset one of the sensors in flight or have an automatic reset. That is not an uncommon situation. What we find is, if that happens more frequently and it happens at critical times, then that impacts the pilot's ability to get the mission done. But over time and historically we have seen that somewhere between 8 and 10 hours is probably about what we can expect and that, according to the warfighters, is good enough.
23 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you for clarifying that. Mr. Sullivan, Dr. Gilmore, would you like to clarify on the 3F software.
24 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. Well, the rate at which these instability incidents were occurring with Block 2B was one every 30-plus hours, and now it is one every 4 hours. And the initial versions of Block 3i don't provide any more combat capability than Block 2B, it was supposed to be rehosting of Block 2B with the new processor. So with regard to whether 8 to 10 hours is sufficient, what you want is a low probability that during a combat mission, which comprise several hours, you want a low probability that one of these upsets that takes time to reset--and several minutes in the middle of a fight is not acceptable--you want the time between these instability incidents to be long enough that you have a very low probability it would occur in a multi-hour combat mission. Whether 8 hours would be sufficient is something that we will certainly be looking at in IOT&E. It was much better than once every 8 hours with the Block 2B software. And again, 3i initially provided no more capability than Block 2B. Now, as we add capability and more complexity in Block 3F, you might see the numbers come down again. Ultimately, operational testing will tell us what is sufficient.
25 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Mr. Sullivan.
26 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. Yeah, I think, depending on the mission scenarios and things like that, it is certainly a critical thing. I don't know if I would want to be a pilot and watch the screen go blank. But it is a spec, I assume, it is a spec that the contractor has, they are in development. We have talked to the contractor and the program office about this and it is a very serious problem. But 2B had issues and they worked through those and I would hope they can do the same with 3i. And I think probably they will be the same thing with 3F. So eventually I would hope that they will work that out and get it to whatever the spec is, which I would hope would support the warfighter. And if they do that--that is why the timing is so critical, because you would want that done by IOCs obviously, you would want to be able to go to IOT&E with problems like that under your belt as opposed to adding that to the burden of the operational testers.
27 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. I am going to ask Mr. Stackley to follow up, but I have a few other questions that I am going to have to get through, but considering this is our last day for votes, I want to be sensitive to members who might need to leave. Since I am the only one on this side, I am going to ask unanimous consent if I let Mr. Stackley respond. And then the order is Mr. Johnson, Gallego, and Ms. Graham. What I will do is I will let each of you ask your questions, and then I will go back to my next question, and then we will finish up, and that way you can exit, if that is okay. Mr. Stackley.
28 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Secretary Stackley. Yes, sir, very briefly. The 2B software is performing very stably and I think everybody is satisfactory with its performance. The rehosting of that software into the new what is referred to as tech refresh on the JSF, the complexity of that rehosting should not be understated. We went through that on this tech refresh. We don't anticipate as large a leap in future tech refresh. But that complexity should not be understated. That did create a reset in terms of stability and now with each such successful build of software going back at building back up the degree of stability that we require. General Bogdan's reference to an 8 to 10 hours at this stage of the program, that probably is satisfactory. In the longer haul, Dr. Gilmore is correct, we want to get this up to a low probability of occurrence such that the pilot does not have to worry about resetting his mission systems mid-flight.
29 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Mr. Johnson.
30 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412199 |  | Mr. Johnson. Thank you, Mr. Chairman. To follow up on your questions about the need for our country to invest in a fifth generation of aircraft to take over from the legacy aircraft that have been flying for decades now, the F/A-18, the A-10, and the AV-8B, would all be replaced by our investment in the F-35 fifth generation. And it is important to note that other nations are investing in fifth-generation aircraft--the Russians, the Chinese--and that is what we mean by a changing threat environment, which America must step up to the plate. And if it intends to remain superior in the air, we must step up to the plate and invest and prepare for the long term. And that is what the F-35 enables us to do. With respect to those who may have participated in the poll that Chairman Turner referred to and were of the opinion that we should extend the legacy fleet and rely on it for our future protection, isn't it--and I assume they want to do that because it saves money. So penny-wise, pound-foolish, that would apply in this kind of a situation here. Isn't it a fact that if America were to do what some prefer, which is to extend the life of the legacy fleet, isn't it a fact that operations and supply costs to extend the legacy fleet would cost approximately four times what operations and support costs would be for the F-35 over the next 50 years? Isn't it a fact?
31 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Secretary Stackley. Well, let me start with responding to that. I don't know about the four times number, but what we do know is that----
32 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412199 |  | Mr. Johnson. Approximately.
33 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Secretary Stackley [continuing]. As our aircraft age, for example the early versions of the F-18 that the F-35 Bs and Cs are going to be replacing, the A through D version, as they age, the cost of sustaining them, the cost of keeping them flying, the availability rates for those aircraft, they are, frankly, hurting us in terms of our strike fighter inventory for today. So we have got to get this next version, generation of aircraft, not just the capability, but also to retire the legacy aircraft that are costing us today. So as that timeline extrapolates out, all the legacy aircraft could be running into similar costs associated with sustaining a fleet that is not just old, but a lot of the sustainment is dealing with obsolete parts and capabilities that fall short of what we require for the warfighter.
34 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412199 |  | Mr. Johnson. Anyone else want to add to that?
35 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. I would just say that I wouldn't focus as much on the cost for O&S. The Joint Strike Fighter is going to be very costly with sustainment too. It is more about the capability. They need that greater capability. The fifth-generation aircraft is really just far superior. I think O&S costs, it would cost a lot to keep these legacy aircraft in the air--I know the Harriers are really old--and eventually they just won't be able to fly them, I would think, after a while. So there is just nothing out there. The F-16 is another aircraft that the F-35 is going to replace. So there is an awful lot of aircraft it replaces.
36 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412199 |  | Mr. Johnson. Thank you. Lieutenant General Bogdan and Secretary Stackley, the Marine Corps declared initial operational capability last year for the F-35B and the Air Force is planning to do the same this year. This, to me, demonstrates a program that is maturing and reaching a point where it would benefit from increased production. Do you agree? And if so, what are some of the benefits and increased production rates for the F-35 program?
37 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Secretary Stackley. Let me start. First, it clearly reflects a program that is maturing. It was mentioned earlier that back in 2010 we restructured the program and within months we are holding to that restructured program's schedule here in 2016 and our costs at the same time are coming down in terms of production while we hold the line on development. The program is methodically increasing its production rates to today in terms of both the U.S. and our international partners and foreign military sales customers joining in that production. So the production rate is methodically increasing. And what we are seeing in terms of benefit is we are accelerating the learning curve on the production floor, it is driving down our costs. And as described earlier, we are seeing positive trends by every measure as it relates to both airframe and engine manufacturing. The longer term, when we complete IOT&E and getting to the full-rate production decision, I think we are on track for that, again, within months, within a budget cycle. And as we march in that direction, we are looking forward to such vehicles as block buying contract and ultimately multiyear contracting to, again, further leverage the benefits of a stable design, mature production lines, and then let's buy it as efficiently as possible.
38 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412199 |  | Mr. Johnson. Thank you. I will yield back, Mr. Chairman.
39 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you, Mr. Johnson. Turning back to the initial operating capability concerns and the requirements for later this year, General Bogdan, in attention to software development I understand that General Welsh is closely watching the progress of the Autonomic Logistics Information System, known as ALIS, as well as challenges facing aircraft software stability which is affecting the radar. As you know, ALIS was a significant area of concern raised by maintainers during our visit to the Eglin Air Force Base last year. Please provide us with a short update on these two issues and what your concerns are concerning the IOC later this year. General Bogdan. Yes, sir. As I said before, within the next 30 days we ought to know if the fixes we have put into the software on stability will take hold. And if that is the case, then we will incrementally upgrade the Air Force's airplanes at Hill Air Force Base with that version of software and the software stability issue will not impact their ability to declare IOC. That is not the case with ALIS. ALIS, the next increment of capability we are delivering, as you know, is 2.0.2, and we were supposed to have that fielded by August of this year. I am estimating that that delivery of that system is probably about 60 days late now. I am not sure if we will be able to pull that schedule back any. If that is the case, then it will be up to the U.S. Air Force to decide what to do in August when it comes to ALIS 2.0.2 if it is going to be about 60 days late.
40 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Does anyone else wish to comment?
41 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. I would only say that we have another team within GAO that is looking and specifically kind of looking at ALIS. And I believe they have a draft report over on the Hill right now. That might be helpful, to look for that. In fact, I can probably make sure that the committee gets a draft copy of that. [The report referred to, GAO-16-439, is retained in the subcommittee files; it can be found online at http://gao.gov/products/GAO-16-439.]
42 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. That would be great. We should, because we had significant concerns for the maintenance group.
43 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. Yeah. So this team is focused really on O&S and ALIS and things like that.
44 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you. General Bogdan. Can I make one other comment, sir, about ALIS, very quickly? If you went to Eglin Air Force Base today or if you went to Luke Air Force Base, what you would find over the past year is not all, but many of the maintenance workarounds and burdens that we placed on the maintainers over the last few years are systematically getting improved. We are not anywhere near where we need to be with ALIS, but I think what you would get from the maintainers if you talked to them today is the fact that they do indeed see an improvement each and every time we put out a new version of software, which means the trending is going in the right direction, we just have a long way to go.
45 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you, General. One thing we know is that consumers weren't given iPhones until they were done. You have to, however, put planes in pilots' hands while you are still developing them. And so we all get to look over your shoulder as you are doing it, and we appreciate both the work of the GAO and others to ensure that we have the right to-do list, but your diligence to try to make certain we complete it. Mr. Gallego.
46 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412612 |  | Mr. Gallego. Thank you, Mr. Chair. General Bogdan, the original concept of the F-35 platform was to retain about 70 percent similarity between the three variants in order to keep costs down on the budget. But as we know, this has not been achieved, which calls the original concept into question. Knowing this, would you support programs in the future that aim for commonality between platforms for the services or do you think these efforts would also have too many cost and schedule overruns? General Bogdan. Congressman, what I have said before about joint programs is that they are hard, they are neither good nor bad, and it really depends on how you manage them. But they are indeed hard, and they are hard because when you bring together a number of different customers that may have varying requirements, it is sometimes hard to meet all those requirements without going to the least common denominator. And so what I would tell you is a decision to move forward on any platform in the joint arena would depend on how much overlap the services see in the requirements that they have. There are opportunities outside of a joint program to benefit from commonality, using similar engines, using similar flight control systems. But to embody that in the same airplane that would try and meet the requirements of varied customers is a really hard thing to do.
47 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412612 |  | Mr. Gallego. I hope we will remember that in the future. Moving on to pilots, though. An October subcommittee hearing discussed the problems with the ejection process for pilots. Two solutions you talked about were developing lighter helmets and managing parachute timing after ejection. However, today we find out the GAO report notes that the helmet weight was not the root cause of neck injuries during ejection. What is the status of the efforts to protect our pilots, one? And with certainty, can you say that we've identified all the problems related to this issue? General Bogdan. Yes, Congressman. One point of clarification. There are two technical issues as to why a pilot less than 136 pounds has an added risk of injury during ejection. One of them is indeed because the helmet is too heavy, but the other is a technical issue having to do with the way the seat fires up and the center of gravity of a light pilot. But both of those problems contribute. We have three fixes in place to remedy this. The first is an ejection seat switch. That will be set by the pilot based on his or her weight. We have tested that. We are in the design phase of it. And that fix will be cut into production on our lot 10, and we will start retrofitting airplanes with that fix in November of this year. We also have a head support panel, which is a pad that will be sewn into the risers of the parachute. That fix has been tested. It too will be incorporated into lot 10 and it will start being retrofitted in November. Relative to the helmet weight, we needed to get the helmet down to about 4.6 pounds. We are in process of doing that as we speak. Originally the estimate was that that helmet wouldn't be ready for fielding until November of 2017. I can report now that that helmet will be available in November of 2016. So when we have the switch, the helmet support pad, and the lighter helmet out there in November, I believe by the end of this year we can remove the requirement of a pilot not being able to fly the airplane less than 136 pounds.
48 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412612 |  | Mr. Gallego. And then just the second portion of my question was, can you say with certainty that we have identified all the problems related to this issue in terms of our pilot safety ejection. General Bogdan. Sir, we have 14 more sled tests and ejection tests to go between now and September. So I cannot tell you right now definitively that we won't find other things. What I will tell you is we will completely test it. If there are problems, we have a good track record of fixing them. Because we will not put pilots' lives in danger by putting them in an airplane and an ejection system that is not safe.
49 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412612 |  | Mr. Gallego. Thank you. I yield back my time.
50 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you. General Bogdan, as you are aware, a lot of our discussions between you and the committee are based upon our visit to Eglin Air Force Base, and the questions that we pose are a result of that fact-finding trip. There were 14 of them. And you have continued to both answer those questions and update them. I have your March 17, 2016, letter in response continuing to update us on those issues. If there is no objection, I am going to enter this into the record of your discussion on these items and the issues that we have been looking for, for oversight. [The information referred to can be found in the Appendix on page 113.] General Bogdan. Thank you, sir.
51 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Ms. McSally.
52 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Thank you, Mr. Chairman. And thank you, gentlemen. I remain a strong supporter of a fifth-generation fighter, having been an airman myself. Knowing the threats that we have that are emanating, we need that capability. However, I remain concerned about the close air support of FAC(A) [forward air controller-airborne] and combat search and rescue missions that are currently being done by the A-10 Warthog and the F-35's capabilities to replace that without increasing risk to American lives. General Bogdan, can you confirm that the F-35 requirements document is still that the F-35 would replace the A-10 and the General Bogdan. Ma'am, what I will tell you is the requirements document that I have on the program does not specifically say that it will replace the A-10 and the F-16. My requirements document has to do with what the capabilities of the F-35 is. The decision to replace airplanes with the F-35 is a service decision.
53 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Okay. I think, though, on the program page, I mean, the intent of the Department, the intent of certainly the Air Force is that the F-35 will replace the A-10 and the F-16. Is that fair to say? General Bogdan. I would believe, from the public statements I have heard from the Chief and the Secretary and the combatant commanders, that is a true statement.
54 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Okay. And I think that is also on the JSF Web site, as well, for the program. On March 3rd, the Air Force Chief of Staff said in a hearing that the mission capability of the A-10 will not be replaced by the F-35. He also talked to me about this after our hearing last week. He went on to say the A-10's current workload would be handled by the F-16 and the F-15E. This was a total surprise to me to hear him say this, to be frank with you. So I am concerned. And I look at their 5-year plan, that they are going to start mothballing more A-10s, next year, 49; 49 the year after that; 64 the year after that; 98 the year after that, finishing in fiscal year 2022. When do you think, again, we are going to be at FOC [full operational capability] for the F-35? General Bogdan. Ma'am, the full capability of the F-35 relative to close air support will be delivered in the late 2017 timeframe. We will have additional capabilities in our block for modernization that would make that mission more viable for the F-35. And I am not sure if the Air Force has declared an FOC date yet.
55 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Okay. But from the testimony, I think, for Dr. Gilmore, I mean, we have seen the F-35A, and we have talked about this in previous hearings, capabilities are limited, 20, 30 minutes time on station; two bombs; you know, excuse my language, but we call one pass haul ass; no time to loiter; having to go to tankers; being Winchester; 182 bullets; limited night capability; inability to get data; targeting information; inability to survive a direct hit in close combat. These are all limitations we know about, we have talked about in previous hearings. So, Dr. Gilmore, I appreciate that your office has decided to do a comparison test between the F-35 and the A-10 on close air support. And I am concerned also about the combat search and rescue and the forward air control mission. Can you give us an update on that comparison test and when that is going to happen and whether there are any concerns about funding or its continuation in another administration?
56 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. First, with regard to requirements, I reviewed the requirements document before I came here. And there is a clear statement at the beginning of the requirements document, which has been in force for a number of years now, that the F-35 would replace the A-10.
57 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. That is what I thought. Thanks, Dr. Gilmore.
58 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. I am happy to send you a copy of that.
59 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Please do.
60 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. In any event, with regard to---- General Bogdan. Can I correct the record? When I talk about requirements on the program, I talk about a specification that I put contractors on to deliver a capability. The document you are talking about is a service document known as an operational requirements document,----
61 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Okay. General Bogdan [continuing]. An ORD, which I do not control.
62 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Okay. Thank you.
63 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. And that's the one the Chief of the Air Force, the Chief of Staff of the Air Force signed----
64 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Great.
65 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore [continuing]. Namely, the operational requirements document. So that is what I was talking about. With regard to the close air support tests, comparison tests, yes, we are planning that. We are planning all the open air tests as we speak, working with the joint operational test team and the services. We expect to have that effort completed in June or July of this year. And we are happy to share those results with the committee and with you. With regard to funding, the costs of the close air support tests, including combat search and rescue [CSAR] and Sandy <dagger>------------------------------------------------------------------------------- <dagger> ``Sandy'' refers to a mission in which an aircraft (most often an A-10) is tasked to support and provide protective coverage for a combat search and rescue mission to recover an ejected pilot behind enemy lines.---------------------------------------------------------------------------
66 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Right.
67 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore [continuing]. Compared to not doing them----
68 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Right.
69 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore [continuing]. You know, compared to not having the A-10s fly, you know, conducting the same missions that the F-35s would conduct in those two areas or those three areas, varies between $3.5 million and $5.2 million. The difference is the amount of refly that you have to do. When you are doing--just like when you are doing a test, you can't count on every scenario that you are trying to run actually working.
70 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Right.
71 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. So you have to plan in the test for refly, the same way General Bogdan is planning for refly in developmental testing. So that is the reason for the range of $3.5 million to $5.2 million. We are working to, with the joint operational test team, to fit all of these comparison tests within the budget for operational testing, which was established, I think, about 5 years ago in the TEMP [Test and Evaluation Master Plan] that is now rather out of date. But, nonetheless, we take that budget seriously. And we are working to fit all the comparison testing within that budget. If there is--if we do go over, which, again, we are trying very hard not to do because we do take that budget limit seriously, it wouldn't be by more than 10 or 15 percent. And I would remind the committee that the Block 2B operational utility evaluation, which was supposed to have been done in 2015, was canceled at my recommendation 2 years ago because it was clear to me that the aircraft wouldn't be ready for that kind of rigorous operational test. And the service acquisition executives agreed. And that was a savings of about $100 million. So we are working to keep within the existing budget and the CAS comparison testing, CSAR, and so forth is, again, a small amount of the overall cost, $3.5 million to $5.2 million.
72 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Thanks, Dr. Gilmore. I am over my time. But could you--when would we be able to have those results delivered to Congress of the tests, do you think?
73 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. Well, if we begin the operational testing, according to my estimate, which would be mid-calendar year 2018, the operational test will compose, will comprise, rather, about a year. It will take about a year. And then it would be a few months after that, no more than 6, hopefully fewer, to actually finish the report.
74 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. So late 2019, early 2020 would be fair?
75 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. Yes.
76 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Okay. Thank you. I appreciate it. Thank you, Mr. Chairman.
77 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you. Mr. Walz.
78 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412214 |  | Mr. Walz. Thank you, Chairman. And thank you all for being here again. We really appreciate it. The strategic need for the F-35, I think everyone knows that. We hear it. It is now crunch time, though, on the delivery piece of it. And, General Bogdan, you are right, there is a perception issue both in what they are going to get and what they expect to get. But there is also this perception that I have held and I have used this as an example. I have been to no less than 14 hearings dealing with changes to retirement plans, taking away of the housing allowance, transferability of the GI Bill benefit, commissary changes, and TRICARE. And where that relates to this is the perception out there is, is when the Pentagon needs to save money, they go to those programs. And I always use the example that we haven't had as many of these. So I hear statements like this from one of our partners from the Australian Defence Force, I think it was Keith Joiner said it. He's responsible for evaluating this, and he said some systems like the radar are fundamentally worse than earlier, which is not a good sign. The next software version Block 4 won't be available. So here we are with bug fixes for the next 7 years. And they are looking, am I correct in this, they are reevaluating their purchases on this. So I go back home. I talk to soldiers and sailors, say, ``So I just lost a GI Bill benefit. What is happening with this?'' How do I talk to them about it? Is it a matter of until you deliver it, this is just going to go on? Because I do kind of feel like I am asked to come into the play and do my part and say this, and then it is going to be delivered. How do I go back? How would you answer on this? General Bogdan. It is a tough question, Congressman. And I clearly understand the point of view here. I guess the best I would offer, if I were asked that question, is that bringing a new weapon system online to defend our country is never easy. And it always is fraught with mistakes, bad choices, technical challenges. And the history of especially developing airplanes has been murky. We have had lots of problems over the years bringing new airplanes online.
79 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412214 |  | Mr. Walz. And that is a helpful piece. You have more experience in this. How similar is this to when the F-16 came on? How similar is what we are seeing here today? General Bogdan. The F-16 was a very simple airplane when it first came out and over the years got more complicated. And it had setbacks. I am not sure if you are aware, the very first flight of the F-16, sir, was an accident. They were not supposed to take off. Because of the flight control system not being properly rigged, the pilot, in order to save the airplane, had to take off. So airplanes experience this.
80 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412214 |  | Mr. Walz. No, I think that is true. And I want to be clear on this so that I am not, and I am not teeing this up, because I am one who believes we need these systems. Is it apples to oranges because of the exponential technical differences between that launch and this launch? And I know that is kind of a hard question because we were at our technological limit then and now maybe we are there, so it may be similar to that. But is it the case that there is more things that can go wrong so they probably will?
81 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Secretary Stackley. Sir, let me jump in and say that is absolutely the case. And it is not unique to the F-35 program. We are going after a high-end capability on this and other warfare systems that are significantly more complex than the systems that they are replacing. So there is no such thing as replacing legacy, whether it is aircraft, missile systems, ships, tactical vehicles, on a one-for-one basis anywhere near the same cost of those legacy systems because these are so much more capable. You know, the comments and perceptions from folks that are not well informed on the program, those are tough to defeat because now you are talking about an education process. The reality is that the F-35 program, albeit it has gone through restructuring, is on a path to deliver all the capability that was promised from day one. It is going to cost more than what was estimated back in the 2002 timeframe. Those costs were rebaselined in 2010. And we have kept those under control to the extent that now we are actually reducing costs with time as the program gets more and more mature. What you are not hearing, and I think General Bogdan touched on this earlier, is the warfighters that are flying this plane, what their perception is. My comment in the opening statement was the Marines love this aircraft, absolutely love this aircraft. This is what they plan to go to war with, if called upon. I think that you are going to hear that overtake the other rhetoric over time as more and more of our Air Force, Marine Corps, and Navy pilots, and our international partners climb into this cockpit, see what its capability is, train with it, and then deploy with it over time.
82 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412214 |  | Mr. Walz. Yes, Mr. Sullivan.
83 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. Your question is an excellent question. And it is not just the F-35 program. It is about the acquisition process. We do acquisition reform all the time. And actually, it has been improving the last few years. But the bottom-line answer to this is there has got to be a little truth in advertising when these weapon systems start up because they are always started up with optimistic cost estimates and schedules. This program was originally planned to be completed, everything purchased, by 2026. Now that is 2038. And so that additional 12 years of funding----
84 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412214 |  | Mr. Walz. And that has as much to do with this side of the table as that side.
85 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Mr. Sullivan. Yeah. So, I mean, and that is what you are talking about, is that the Congress is faced with unplanned, you know, funding for 12 years that they weren't planning on when they started. Like I said, it is not the F-35, it is most of the major weapon systems. They just don't have a good business case at the outset. The F-16 was a really good aircraft when it was delivered, and it was simple. And it is not that simple anymore. It is a very complex aircraft because they planned it properly. They had incremental planning on that and they did block upgrades. That is really what, I think what this is all about. And so other priorities go by the wayside.
86 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412214 |  | Mr. Walz. I know. Well, thank you. I yield back. Thank you, Chairman.
87 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Ms. McSally.
88 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Thank you, Mr. Chairman. I do just want to follow up on our discussion on requirements, just to make sure. Luckily, I flew airplanes, I never had to procure them. So this process seems a little cumbersome to me. But just, Dr. Gilmore, an Air Force Chief of Staff has said that the A-10 will not be replaced by the F-35, on the record, within the last few weeks. And then said that to me in a conversation last week, surprising me. Is the Air Force going to be updating their ORD, or whatever you just called it----
89 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. The operational requirements document? I haven't heard that they are.
90 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally [continuing]. To reflect that?
91 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. I haven't heard that they are. And then the F-35s are going to be replacing the F-16s.
92 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Right.
93 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. So I am a bit puzzled. But all I know is what the existing operational requirements document said.
94 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Okay. So you know of no efforts to update that. And if it is currently----
95 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. I am not aware of any.
96 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally [continuing]. Going to be replacing the A-10 and the F-16, but he is saying the F-16 is going to replace the A-10, but then the F-35 is going to replace the F-16, then we are still in the same situation where we are. In specific circumstances for close air support, we potentially have additional risk or a gap or capabilities that are going to be degraded, which is why it is so important that we have this flyoff. Do you agree, Dr. Gilmore?
97 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. Well, you know, I don't know whether the capabilities will be degraded.
98 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Right.
99 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. That is what the comparison testing is supposed to find out.
100 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Absolutely.
101 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | N/A |  | Dr. Gilmore. And that is why we are planning it to be, you know, absolutely fair. We are going to consider all the conditions under which close air support are done, all the different kinds of threats. And it certainly will be a challenge. In fact, the A-10 couldn't survive in the highest threat environments. But we are also looking at, you know, less stressing threats like the ones that the A-10 is being used in, the environments it is being used in today: urban, rural situations, buildings, vehicle personnel, different kinds of control for the close air support, different kinds of control interaction, all of the things that you know are done in close air support missions. We are going to set up the missions. And then the A-10 pilots and the F-35 pilots will use those two aircraft to their best capabilities, using whatever TTPs [tactics, techniques, and procedures] they have. We are certainly not going to specify how the missions are done. We are going to specify what the mission is. And then we will do matched pairs comparisons of how well each set of pilots and aircraft can perform those missions the way they choose to.
102 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 412611 |  | Ms. McSally. Great. Thank you. And it seems like there is just some different messages coming out of the Pentagon. I mean, the Secretary of Defense, when he announced his budget, said A-10s will be replaced squadron by squadron, with the F-35 predetermining the outcome of this test. So we are trying to get some consistency out of the Pentagon by just asking these questions. I highlighted this to the Secretary yesterday. We are going to follow up with him and the Chairman. Because it just seems like even between the Air Force and the Secretary of Defense, they have got two different messages going on here. We believe that any movement forward should be conditional. Let's have the test. Let's get the results of the test. And then let's make a decision afterwards as to whether we are going to be increasing risks to our troops on the ground. So I appreciate the additional time, Mr. Chairman. Thank you, gentlemen. And I yield back.
103 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg20078.txt | 118] HEARING ON NATIONAL DEFENSE AUTHORIZATION ACT FOR FISCAL YEAR 2017 AND...' | 400411 |  | Mr. Turner. Thank you. Gentlemen, this is one of our most important and certainly largest programs. And I want to thank each of you for your diligence in trying to ensure that this program reaches all of the capabilities that are obviously going to be necessary. Because of that, before we conclude, knowing your diligence, I want to give each of you an opportunity if you have anything else that you want to put on the record or that you want to raise before the committee as we consider this, knowing that your input is incredibly important. If not, I know we have your opening statements. And we continue to have your advice and counsel. We appreciate the information you have provided to the committee. Thank you.