## Sheet1
| committee_name | committee_code | file_name | title | govtrack | speaker | speech
0 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. The Armed Services Tactical Air and Land Forces Subcommittee meets today in open session to receive testimony on the current status of the F-35 Joint Strike Fighter, JSF, program. This hearing continues the ongoing oversight activity conducted by the committee on the F-35 programs. The program officially began in 2001. We welcome our distinguished panel of witnesses. We have Dr. Michael Gilmore, Director of Operational Test and Evaluation [DOT&E]; Dr. Michael J. Sullivan, Director of Acquisition and Sourcing, Government Accountability Office [GAO]; the Honorable Sean Stackley, Assistant Secretary of the Navy for Research, Development and Acquisition; Lieutenant General Christopher C. Bogdan, F-35 Program Executive Officer. I thank all of you for your service and look forward to your testimony today. The F-35 is a complex program. It is well known that, during its development, the F-35 program has experienced significant cost, schedule, and performance problems. Current acquisition costs are now approaching $400 billion, which, according to GAO, makes this DOD's [Department of Defense] most costly and ambitious acquisition program. Over the last year, steady progress was achieved in development, production, and operations, but the subcommittee continues to have concerns regarding recent engine test failures and on software development and integration. This committee, in particular this subcommittee, has maintained vigilant oversight on the F-35 program through legislation, hearings, and briefings, and, most recently, a trip to Eglin Air Force Base, Florida, to see the F-35 operations and talk to F-35 pilots and maintenance personnel. Last year the committee required the Secretary of Defense to establish an independent team to review and assess the development of software and software integration for the F-35 program. This subcommittee may recommend a similar approach as a way to effectively review the most recent engine test failures. I understand the substantial investment in the F-35 is more about the requirement for fifth-generation tactical fighter capability than it is about the F-35 itself. And let me underscore that. All of the members of this subcommittee are very well aware of the need for fifth-generation tactical fighter capability and the need to ensure that the F-35 is one of the most capable aircraft. Based on the briefings and hearings held by the subcommittee, I have learned that fifth-generation tactical fighter capability is essential for maintaining air dominance and national security. Despite this critical need, that does not mean that this program should be rubber-stamped. As we have done in the past, the committee will hold this program accountable for cost, schedule, and performance. The budget request for fiscal year 2016 includes $1.8 billion for F-35 research, development, test, and evaluation and $8.7 billion for the procurement of 57 F-35s, and $410.2 million for spares. This represents an increase of 19 aircraft and is also a $2.5 billion increase in F-35 funding from the fiscal year 2015 enacted levels. And we all understand that we need to get to a higher production level to get the lower per-unit cost. We also understand that we have to address the issues operationally for the F-35 to ensure its best capability for the pilots and its intended needs. We will hear today both the Director of the Operational Test and Evaluation and the GAO have concerns about the F-35 program for fiscal year 2016 and beyond. I look forward to all of our witnesses' testimony today, which will provide for a better understanding of the current status of the F-35 program. [The prepared statement of Mr. Turner can be found in the Appendix on page 33.]
1 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Before we begin, I would like to turn to my good friend and colleague from California, Ms. Loretta Sanchez, for any comments that she might want to make.
2 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400356 |  | Ms. Sanchez. Thank you, Mr. Chairman. And thank you for calling this. I think this is an incredibly important project for us. So we are looking at the 2016 budget request for the F-35 Lightning II aircraft program. It totals $10.8 billion spread across 17 separate procurement and R&D [research and development] accounts. That is an enormous amount even by the standards of the Department of Defense's budget. The total is, for example, more than the Navy's fiscal year 2016 request for aircraft carrier and submarine construction combined. It is five times as much as the Army's fiscal year 2016 request for weapons and tracked combat vehicles. So given the scale of this proposed funding, I think it is important that we try to understand what is going on with the program. Since World War II, America's way of war has required air superiority. And so airpower is one of the great advantages that we give to our military, especially when we are in places and it has proven time and time again. So the F-35 program, while flawed to this point, is really the key to retaining that airpower edge for the next 20 years or so. It is also going to be flown by at least 12 allied nations, all of whom are likely to be our partners in future conflicts at some point. And so there have been some critics who have said we need to terminate this program because it is over cost, it is long overdue, and there are still problems with it. However, I believe that we are past that decision point. We have just got to make this program work. And I think you will agree with me, Mr. Chairman, we have had many discussions on this. We have got to get this done. Making it work is not an easy task. It is a very complicated piece of machinery, and everybody's had their fingers in it. Lots of decision have been made, and lots of decisions have been changed. I am very still concerned about the engine fire last year, which resulted in a setback in the testing schedule. The substantive grounding also highlighted the risk of the current sole-source engine production arrangement that this program depends upon. Secondly, the highly sophisticated software for the F-35 continues to encounter developmental delays. Both the GAO and the DOT&E have pointed out in their most recent reports that, because of the pressures on the flight testing schedule, a significant amount of test points were deferred or entirely dropped. More specifically, the committee was recently informed by the F-35 program office at the start of development flight testing of some critical elements of the Block 3F software effort are on hold indefinitely, pending more progress on the critical fusion element of the preceding Block 2B software. In addition to its stealth characteristics, the ability to fuse sensor feeds from other F-35s and other sources is one of the most important parts of the F-35 program. So, of course, this delay is also troubling with respect to the program. And the operating and maintenance: The sustainability is significantly different than when we envisioned this project on the drawing boards. The GAO report noted in particular that the F-135 engine is far below reliability targets and that, as a result, the overall availability of the F-35 continues to lag significantly behind expectations. I know that, when we have had other aircraft, new aircraft, we have had some of the same problems, not to this extent, not in this size, but we do need to get past these issues. So given all of these challenges and the very large funding request for the F-35 that we are faced with, I think it is important in today's hearing. And this is what I would like to hear about: Is the proposed increase in F-35 production numbers, which would rise from 38 in fiscal year 2015 to 57 in fiscal year 2016, justified, given where the program is in development? What would a reduction in the numbers of aircraft look in particular to this program? Second, we need a detailed review of what happened with that engine fire last year. I have been asking for it. I haven't heard it yet. We know that the aircraft and the engine in question were relatively new, yet a failure still occurred. Is it a manufacturing defect? Is it a design flaw? I would like to hear about that. Third, the sensor fusion aspect of the F-35 software is a little understood, but critical, issue that is still not working as planned. What degree of risk do we face with that portion of the software? And could problems in this area turn what is the current delay of about 3 to 6 months into years? So I look forward to getting some of the answers to these questions, gentlemen. Thank you. And, Mr. Chairman, thank you for indulging me with the time.
3 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. We will begin with Dr. Gilmore, being followed by Mr. Sullivan, Mr. Stackley, and General Bogdan. Mr. Gilmore.
4 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. Thank you, Mr. Chairman and Congresswoman Sanchez and members of the subcommittee. I will just briefly summarize my written testimony. Block 2B testing was extended, but is now nearing completion. The program developed an additional build to the Block 2B mission system software designed to incorporate fixes to problems, particularly in fusion of information both from the sensors on an individual aircraft as well as from the sensors on other F-35 aircraft that were highlighted in testing that was conducted in December of last year and early in 2015. This so-called engineering test build was flown on 17 test sorties using 3 different mission systems to test aircraft in March. And although some improvement in performance was reportedly observed, distinguishing ground targets from clutter continue to be problematic. And given the limits in the improvement seen using this engineering test build, I understand the program has decided to field the current, that is, prior to the engineering test build version, of the Block 2B software as opposed to waiting and doing additional testing with the engineering test build and to defer fixes of the software to Block 3i development and testing. If the balance of 2B testing completes in April, this would represent a delay of about 6 months relative to the program's master schedule. Modification of early lot aircraft into a configuration usable for combat with Block 2B capabilities, a necessity brought on by the concurrency in the program, which dates to the program's initiation back in early last decade, is taking longer than planned and longer than predicted when the Department eliminated, on my recommendation, the block to the long-planned Block 2B operational utility evaluation [OUE]. These delays, as well as other problems that motivated the extension of Block 2B testing, indicate clearly that the aircraft would not have been ready to conduct the OUE by beginning training with operational pilots this past January and convinced me that the recommendation I made, which was adopted, was the correct one. The trends and reliability metrics we track are unclear. The most recent data we have obtained generally indicate, with the exception of mean flight hours between critical failure for the F-35B, a 3-month upward trend, which is good, from September 2014 to November 2014. However, when combined with data from the previous 3 months, they showed both declines and increases. Thus, I cannot yet conclude with confidence that reliability is continuing to improve. Aircraft availability did show improvement at the end of 2014, as the program focused on providing greater supplies of spares and on shortening maintenance activities that had heretofore required longer aircraft downtimes. However, that trend has not been sustained so far in calendar year 2015, as the first 2 months have shown a decline. But, again, that is only 2 months. We shouldn't rush to conclusions about whether that constitutes a trend. I have also updated my analysis of the growth and reliability needed for the F-35A and B variants to achieve their requirements based on the most recent data from November 2014. And that analysis indicates that growth and selected reliability metrics for both aircraft, the A and the B, remain insufficient to meet requirements of maturity. And there is insufficient flight hours in the C variant to preclude that--I can't do meaningful analysis at this point in development. It is still too early. Discoveries in testing continue to occur, which should be expected in a program of this complexity, such as was highlighted regarding sensor fusion, as well as the occurrence of additional unpredicted cracking in the F-35B durability test article, which was discovered in February and caused testing to pause until repairs could be completed. Testing did restart on the 1st of April. Flight testing of Block 3i mission systems, consisting of a Block 2B software we hosted on the upgraded set of processor hardware needed before Block 3F software can be used, we started March. And one of the mission systems test aircraft began testing the next increment of software that is called 3iR5. Block 3F flight testing also began in March, what was limited to three single-ship test flights on one mission system's test aircraft, AF-3, prior to it being reconfigured to support late Block 3i testing. This start represents an 11-month delay relative to the program's master schedule and about a 1-month delay relative to the program's more recent projections. Continued Block 3F testing is not scheduled until June, as the program's plans for reconfiguring aircraft in the Block 2B configuration to Block 3F are under development. In both my annual report and my written testimony, I identified problems with the U.S. Reprogramming Laboratory, which is the government facility that is going to be used to generate what are called mission data files for the aircraft--mission data loads for the aircraft. These data loads are essential to the effective combat operations of Joint Strike Fighter. I had identified 2 years ago shortfalls in those labs. The program office has done a study that reconfirmed those shortfalls and found new shortfalls. About 2 years ago the Secretary of Defense provided resources to correct those shortfalls, but no action has been taken. It is my understanding, if the program office takes action very quickly, those shortfalls can be corrected in time for operational testing and, more importantly, for full operational capability, and I recommend strongly that that action be taken. In my annual report and written testimony, I provided no review of Block 2B capabilities and limitations. The program has identified and prioritized many deficiencies for correction. Nonetheless, Block 2B aircraft will be fielded without a number of corrections of operational significance in place. Further discovery of problems is likely, in my view, as operational units start using JSF in ways it has not previously been used. I agree with the program's assessment that there is at least 6 months' pressure in completing Block 3F, recently projected by the program to complete testing in May 2017. While the program has worked hard to reduce the bow wave of what it calls technical debt, which are fixes to problems that were deferred from earlier mission software versions to later versions--and that continues to happen--the program is now deferring fixes, including problems with fusion and testing to Block 3i and Block 3F, which, together with the delays that have occurred in starting Block 3 testing, increase risk on the program's projected Block 3F schedule. Thank you. [The prepared statement of Dr. Gilmore can be found in the Appendix on page 35.]
5 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Mr. Sullivan, who hails from the great and historic Wright-Patterson Air Force Base.
6 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Mr. Sullivan. Sorry about the Flyers this year, although they made it.
7 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Mr. Sullivan. Chairman Turner, Ranking Member Sanchez, and members of the subcommittee, thank you for inviting me here to discuss our work on the F-35. Let me begin by providing context for where we are today on the F-35 by briefly revisiting the past. As we all know, the program's overall cost has nearly doubled at this point since the program began in 2001 and its dates for delivering initial capabilities have been significantly delayed. No one would argue that these problems can be traced to decisions made then to start the program with little knowledge about technologies, designs, or capabilities needed for this fifth-generation fighter aircraft. A highly concurrent acquisition strategy over the next decade resulted in costly airframe redesigns and significant software and hardware design changes that cascaded onto the manufacturing floor and created more inefficiency. In 2012, the program experienced a Nunn-McCurdy significant cost breach and the Department took significant action to bring realism to cost estimates, add resources to the program, and all in all establish a new baseline for cost and schedule moving forward. So today the F-35 is on much firmer footing and is being managed in a way that has stabilized its cost. It is improving its ability to deliver aircraft more efficiently, and, most importantly, it remains the centerpiece of the Department's long-term tactical aircraft inventory and one of its highest priorities. As we move into the future, it would be nice to be able to report that all risk is now behind the program. However, with around 40 percent of the developmental flight tests remaining, the program has already procured 179 F-35s and plans to add 339 more over the next 5 years for $50 billion, all before flight test is complete. This concurrency between testing and buying more aircraft is risky. Recent problems with airframe durability testing and the engine, continued delays to software development and testing with the most complex portions of that software development yet to come, and other competing national security priorities which will take funding as well, all add to the significant risk that remains and will be needed to be managed very carefully. The recent unanticipated engine and bulkhead failures are prime examples of the program's ongoing struggle with concurrency and the cost and schedule risk it brings. Programs in developmental testing should expect to encounter discoveries that require design changes, just as Dr. Gilmore stated. However, in a concurrent testing and procurement environment, the destabilizing effects of these tests discoveries are amplified as more systems are produced and delivered, thus requiring costly design changes, retrofits, and rework. Given these ongoing challenges, it is important that the program, the Department, and the Congress fully understand the implications of increasing F-35 procurement rates in the near term in order to make informed funding decisions. In our estimation, the Department should provide answers to three critical questions: First, are major test discoveries and design changes behind the program, given that testing of more complex software and capabilities still lies ahead? Second, has the contractor's manufacturing capability and industrial base progressed enough to meet the proposed increased production rates? And, third, is the program's current procurement plan affordable when viewed within the context of competing fiscal priorities both within and outside of the Department? Mr. Chairman, members of the committee, that concludes my oral statement. I would be pleased to respond to any questions. [The prepared statement of Mr. Sullivan can be found in the Appendix on page 59.]
8 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Thank you. Mr. Secretary.
9 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Secretary Stackley. Chairman Turner, distinguished members of the subcommittee, I thank you for the opportunity to appear before you today to testify on the F-35 Joint Strike Fighter program. The Marine Corps variant of the Joint Strike Fighter is on track to achieve its initial operational capability, or IOC, this summer. This milestone is, of course, but a way point, for the software build called Block 2B, which the Marines will employ at IOC, provides limited warfighting capability in accordance with the program's long-planned incremental build plan. Full warfighting capability, at least sufficient to support the final, of the services and our international partners and our foreign military sales customer nations IOCs will be delivered in a subsequent software build called Block 3F. That notwithstanding, it should not be lost on this subcommittee, the significant challenges and adversity that the program has and will continue to overcome in order to achieve the Marines' IOC and that the milestone will be achieved more or less in accordance with the budget and schedule established by the program about 4 years ago. Today, increasingly, the focus is on delivering the next block of capability, Block 3i, which incorporates upgraded computing hardware, but otherwise is the warfighting equivalent of Block 2B, and, therefore, assessed as relatively low risk. We have begun flight testing with Block 3i, and today we assess that we are on track to support the Air Force IOC with Block 3i capability in the summer of 2016. Completion of the final block of capability, Block 3F, which is the capability that the services will ultimately deploy with, poses the greatest challenge to completion of the system development phase of the Joint Strike Fighter program. Block 3F software requirements are well understood and stable. However, this block includes the most complex functionality of the three software baselines, including what is referred to as sensor fusion. Further, coding and testing of Block 3F has been delayed as a result of the resource demands, software engineers, and lab facilities associated with supporting completion of earlier software builds. These factors add up to the program's estimate of 4 to 6 months schedule risk with completion of Block 3F. Despite the schedule risk, we remain on track to support the Navy carrier variant IOC with Block 3F in 2018. In parallel with completion of the system software and related flight testing leading to each of the service's IOCs, the program is managing the resolution of technical issues that have been discovered in testing; the ramp-up of production of the three aircraft variants across a large and growing industrial base that supports JSF; improvements to affordability and production; incorporation of modifications to correct deficiencies identified on earlier production aircraft; needed improvements to reliability and maintainability of the aircraft; planning and assignment of maintenance, repair, overhaul, and upgrade, or MRO&U, responsibilities across the global regions where the JSF will operate; and formulation of the program operations and support strategy with its own focus on affordability. To briefly summarize, today's scorecard on technical issues largely reflects a large list of issues that are well understood with fixes either under development or in various stages of implementation. That said, we are wary that further technical issues are certain to emerge as we press on with system testing, and it will be critical that the program rapidly correct these deficiencies while mitigating their impact on test and production. The most notable technical issue which emerged this past year, a rub condition between the engine rotor and rotor seal, led to an engine fire and brought flight testing to a standstill for several weeks while the root cause of the issue was being determined. We are confident that this technical issue is resolved and are proceeding with implementation of the fix across the fleet of affected aircraft. Aircraft production is demonstrating healthy labor learning curve performance, improving quality trends, improving schedule performance and lot-over-lot unit cost reduction. This is as expected for a program at this stage. To spur a greater cost improvement, the program, led by an industry initiative, has launched an effort referred to as Blueprint for Affordability, which has established a target unit cost for the F-35A of about $80 million by 2019. We are embarking on similar concerted efforts in order to improve aircraft reliability, maintainability, and availability, or RM&A. Overall, performance in this area has been poor. It is only in the past 6 months that improvements to design, parts availability, and maintenance, training, and support are starting to show needed results, providing a positive sign that we may meet our interim RM&A requirement of 60 percent aircraft availability by year's end. RM&A is a principal focus area for the program in 2015. Lastly, the program is working closely with the services and our international partners and industry to formulate the operations and sustainment, or O&S, strategy for the Joint Strike Fighter. The effort encompasses activities stretching from completing development of logistics tools, to standup of depot facilities, to supply chain management, engineering and software support, and determination of the business plan that will accompany each of these activities and an overarching O&S war on cost. In summary, while maintaining its focus on achieving the services' initial operational capability milestones, the JSF program is also systematically tackling a large number of risk items and issues that confront this program across the full spectrum spanning development, test, production, operations, and sustainment. We are experiencing improving trends in virtually all areas, but we are painstakingly aware of the significant challenges that remain ahead and are committed to meeting those challenges head-on with discipline, with rigor, and with full transparency. Mr. Chairman, we look forward to answering your questions. [The joint prepared statement of Secretary Stackley and General Bogdan can be found in the Appendix on page 72.]
10 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. General Bogdan. General Bogdan. Chairman Turner, distinguished members of the committee, thank you for the opportunity to address you and to discuss the F-35 Lightning II program. My overall assessment of this very complex program is that we are making slow, but steady, progress on all fronts and each day the program is improving. However, this is not to say that we don't have risks, challenges, and some difficulties, but I am confident we will be able to overcome these problems and deliver on our commitments. Today, in development, we've completed our Block 2 software development and are nearing completion of all flight testing necessary to field our initial warfighting capability, also known as Block 2B, which is on track to support the Marine Corps IOC this summer. Additionally, we are currently in full-swing testing of our Block 3i software, which is on track to support Air Force IOC in the summer of 2016, and we have just begun flight testing our final version of software known as Block 3F, which will provide the full combat capability of the F-35 in late 2017 and support the U.S. Navy's IOC in 2018. However, because we have been using our labs and test aircraft to complete both 2B and 3i testing for longer than we anticipated, flight testing of Block 3 was delayed. This delay, along with the complexity of the 3F software integration, has resulted in an additional risk of approximately 4 to 6 months for the completion of that 3F software. We are working hard to bring this potential schedule delay back in on time, and we do not believe it will impact the Navy's IOC in 2018. We have had numerous accomplishments in 2014 in flight testing, most notably the F-35C initial sea trials aboard the USS Nimitz, a large-deck carrier. Our performance on the Nimitz in terms of carrier landings was excellent in that we completed 124 traps out of 124 attempts without a single missed landing and we completed all the planned testing on that ship with about 3 days to spare. Additionally, we have closed and are implementing fixes for a number of past technical issues, including improvements in the helmet, the hook on our C model, our fuel dump capability, our fusion software, lightning restrictions, and night and all-weather flying. However, this past year presented other challenges that included an engine failure on AF-27 at Eglin Air Force Base and the discovery of cracks in the main bulkheads of the B model during our durability testing. We are also carefully monitoring the development of our maintenance system, known as ALIS [Autonomic Logistics Information System], as it remains on the critical path for U.S. Marine Corps IOC, Air Force IOC, and our Block 3F capabilities. I am prepared to provide details of these events and the impact they have had on the program or may have on the program during the Q&A [question and answer] period. As for production in 2014, we planned to deliver 36 aircraft and we delivered 36 aircraft to our warfighters. We have now delivered a total of 130 aircraft to our operational test and training sites. The production line today is running approximately 2 months behind, but it is catching up over the past year and does not pose any long-term schedule or delivery risk to the program. The price of the F-35s continue to decline steadily lot over lot, just as we have committed to, and I expect such reductions to continue long into the future. Let me turn to fielding the sustainment of our fleet. As of this week, we have logged over 30,000 flight hours and flown over 18,000 sorties since our first flights in 2006. Today 130 F-35s are operating at 9 different U.S. locations. In the next 4 years, we will add 322 airplanes and over 17 new bases, including operational locations in Europe and the Pacific. Over the past year and a half, we have put a great deal of emphasis on maintenance and sustainment activities. We started a reliability and maintainability program last year, and the effort is beginning to make a positive difference, as we have seen a steady, but slow, improvement in our aircraft availability rates and our mission-capable rates. We also started a number of initiatives to address our spares issues, including better forecasting, more timely purchasing and contracting, and shortening repair cycles on our parts, all of which resulted in modest improvements thus far, but it will take at least another 6 to 12 months to fully recover from our spares deficit. We also began a number of other important initiatives late in 2013 and 2014 to include our ops and sustainment Cost War Room, the Blueprint for Affordability, as Mr. Stackley mentioned, and a restructuring of the operational test program. I would be happy to discuss these initiatives in the Q&A session, also. On the international front, the partnership remains strong and some of our partners are now flying their own jets in training and operational test sites in the United States, while others are eagerly anticipating their first jets in the next two lots of airplanes. Additionally, last year South Korea signed a letter of acceptance and committed to buying 40 jets and Israel committed to an additional 14 jets on top of the 19 they are already purchasing. I would like to close by saying that the program is showing steady improvements as costs continue to come down, technical issues are being resolved, and the baseline schedule is mainly holding. I believe the program is on the right track, and we will continue to deliver on our commitments we have made to warfighters, the taxpayers, and our allies. My team will continue to run this program with integrity, discipline, and transparency, and I intend to hold myself and my team accountable for the outcomes on this program. Mr. Chairman, I look forward to the Q&A period. [The joint prepared statement of General Bogdan and Secretary Stackley can be found in the Appendix on page 72.]
11 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Thank you, General. Secretary Stackley, General Bogdan, a group of us went down to Eglin Air Force Base 2 weeks ago or so and sat down with both the pilots, the maintainers, the command, to discuss the F-35. And, as you know from my opening statement and that of the ranking member, you have full and complete support from this subcommittee and the committee on fifth-gen development. We certainly understand some of the difficulty overall with concurrency. And, you know, it is a vogue word to mean inventiveness. Right? I mean, at the same time that we are building, we are inventing and we are trying to have a fluid process so we don't end up with a product that is stale but, at the same time, we end up with a product and we don't merely get stuck in the inventive process. How those two converge is where Mr. Gilmore and Mr. Sullivan continue to provide us with fidelity as to how problems result. And the issues that we see in both their reports are obviously when a problem is identified, how quickly is it resolved; when a problem is identified, what is its effect on cost; when a problem is identified, how does it relate to our foreign partners and the delays, as we know, because we have to get to a ramp-up so that our overall product costs go down on a per-unit basis. Our trip was not in questioning the overall fifth-generation commitment or capability, but to talk to those who were on the ground to get some understanding of their perspective. Some of the things that we learned were disturbing and concerning. As you know, they are down there both actively flying, actively maintaining, actively training, and then being what will be the footprint later as the F-35 is expanded elsewhere. But one of the issues I want to talk to you about and I want to get your feedback is the Autonomic Logistics Information System, ALIS. So we had a treat. We got to sit down and watch someone actually go through the web pages of the system--and I am slowing down for effect because that is what we got to see as they got to it--and the cumbersomeness of the difficulty of going from page to page in trying to be able to enter information. Now, the ALIS system--real quick overview--is basically the system that you plug the plane in and it is supposed to tell you what is wrong with the plane and what is not wrong with the plane. It is supposed to aid maintenance. It is supposed to give a download for logistics for acquisition of parts. It is supposed to do an overall assessment of the readiness and capability of the plane. But we are also told it has an 80 percent false positive. They went through the process. They were telling us the purpose of the system. It sounds absolutely wonderful. Certainly I think everybody who has a Cadillac understands, you know, a system that tells you what is going on with your car, what is going on with your plane. When we asked them how many false positives you get, I thought that they were going to tell us a high number because it is still a new system. But when they said 80, I was kind of taken aback. But then, when they showed us how difficult it was to clear 80 because of the cumbersomeness of the system, I was curious as to who is assigned to clean this up. But what we probably have with false positives, as you know, is, one, either people get complacent and believe things are false positives and they get overly cleared or, two, we also don't know what false negatives we have and was the system not reporting. So I would like both of you to tell us: Is what we are hearing consistent with what you are hearing? If so, what is the path forward in fixing the system and how does it represent an operational issue or impediment overall to the F-35?
12 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Secretary Stackley. Yes, sir. I will start and hand it over to General Bogdan. I don't know if the 80 percent number is exactly right, but the issue of false positive is very real. And concerns with regards to the reliability, the responsiveness, the timeliness of ALIS information for the maintainers and for the warfighter is at the top of our priority list. We scorecard readiness for initial operational capabilities, and we look at all the attributes associated with the program. And when you look at the services' IOCs as rated by the program office and as rated by the services themselves, ALIS's performance is a very high concern, high priority, because it is not currently meeting the requirements of the warfighter in terms of the maintainability aspects on the program. So it is a real problem. It is a known problem. The solution is not a single, simple issue. It is going after all the details inside of ALIS. It is a large, complex logistics, software-based system. And we have been on this path for several years now, since it was first introduced and put in the hands of the maintainers, and they identified the issues with everything from data reliability to timeliness. And this false positive issue has been brought to our attention more recently. So there is versions of software upgrades to ALIS that are planned that capture the known deficiencies. They are tested before they are turned into the field. And then, when they are put in the hands of the maintainers, we get that user feedback. So I will tell you that the program is improving. It is not where it needs to be. Our scorecards--right now you will see red next to ALIS, which has our absolute attention. And we have got a lot of work to do, but there won't be one leap from that red to that green. It is going to be a series of upgrades to ALIS software where we are going to have to drive in those incremental improvements to get it up to the level of performance that we need.
13 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. One footnote and then I am going to do a follow-on on A-L-I-S or ``ALIS,'' as you were saying. I was also shocked that there is no spell check. So while the gentleman was there typing something in, there was no indication that something was misspelled, but he had to catch it and he had to go back and fix it. My concern is not an academic one. My concern was--because human error is human error--it is not searchable if someone makes a typographical error. If the system is supposed to be searchable, we have got to determine what is recurring in the system. So certainly that should probably be an addition to it. But the other aspect was, as I was describing it, the downstream aspect of A-L-I-S or ``ALIS'' issuing a report for a part. They are very concerned about that whole system, both with the prime contractor's scale of control, the availability of those parts, the reporting back of the availability of those parts. If there is no inventory on site, they are very concerned of the ability of their planes to continue to be able to operate and how the system itself--because it is assuming that they are not going to be able to fix it on hand and it is going to report a problem and then result in a part being delivered, that that just-in-time aspect may be a constraint on overall operation capability. Do you have concerns there, also? General Bogdan, you are nodding.
14 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Secretary Stackley. I will tell you that that is evolving. There was a vision for what ALIS would do and how this program would be sustained that was established years ago. We are past that point today. And the operation and sustainment plan for the program is evolving and being developed today with industry, with our international partners, frankly, to do better than what you are hearing from the maintainers today on the flight line.
15 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Thank you. I am then going to Timothy Walz.
16 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. Thank you, Mr. Chairman. Thank you all for your testimony. I do agree that the importance of this weapon system as to our airpower and our national security strategy is pretty clear to everyone. I also appreciate your optimism, but I don't think we could come here without the skepticism that is probably healthy in any endeavor that we do. So just a couple of things I would ask. And I am going to build on this last question on long-term viability and sustainability because the issues we are talking about are just getting us to the baseline and where we go from there. And so, Mr. Sullivan, on several occasions, I think you have been thoughtful about it and raised long-term affordability as a key area of risk. Is that addressed? Do you see that moving in the right direction? And do you still consider--I think it is obvious and wise to think that way. But where are we headed with it?
17 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Mr. Sullivan. Yes. I think there is two separate things. There is the cost estimate on the program, which is approaching $400 billion. I think that is in control. The software issues we are talking about are going to add cost on the margins, I believe. It is mostly an issue of risk, of being able to do what they say they are going to do. The affordability issue, from our point of view, is the funding profile that this program--that the Congress, quite frankly, is looking at over the next 20 years just for acquisition, just for--development cost is coming down now. I think development cost will be done in 3 or 4 years. But over the next 10 or 15 years, this program is going to come to the Congress every year with--we mentioned today it is $10 billion for this fiscal year. That will get up to $15 billion in a few years, and it is going to average $12.5 billion beyond the foreseeable future. What typically happens is that past programs that begin to run into these kind of funding issues--usually, at some point, if other national priorities have to be taken care of, there is a lot of big weapon systems that are vying for the funding. The Navy and the Army and the Air Force has its own. The tanker is one. Long-range strike is one. Something has to give, and a lot of times it is quantities. You know, you get to a point--the F-22 is an example where they wanted to buy 750 and the funding profile was so straining that they wound up having to cut quantities.
18 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. Is there anything that indicates to you--because I would say the members sitting here understand from sequestration to national debt, to competing priorities, nothing is going to change that. I think the estimate is over, if you will, a 50-year lifecycle of this is $1 trillion. We are not quite halfway there yet. The fortitude to come back every year is one that I think we are going to have to think about and think about deeply.
19 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Mr. Sullivan. Yes. I was just talking about the acquisition cost. Now, when you include the total ownership cost or the operation and support cost, which is right now estimated anywhere from $850 billion to a trillion dollars over 30 years, that is cost on top of that. So some of this discussion about ALIS is interesting. Because one of the things that the Joint Strike Fighter was supposed to be able to do was have a lot of commonality across a variance and reduce a footprint, and it hasn't really come out that way. There were a lot of technologies they were counting on early in this program that I don't think they have been able to achieve.
20 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. And I realize how difficult this is. But I can't stress enough, if it falls short in any way of achieving these things, the difficulty on those dollars are going to be even more. I mean, it has to do everything that it says it is going to do. And so I am going to ask--and I know this is subjective, but I think it is important for us because this is looking ahead--what is this hearing going to look like in April of 2016, when we come back and hold this hearing on the F-35? How big of difference are we going to see? Is this thing going to be doing what it is supposed to do?
21 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Secretary Stackley. I will take that. I will start. A year from now we will have the Marine Corps--we will have IOC, their version of the aircraft. We will be working on completion of 3i testing and will be heavy into the 3F testing. I think, as Mr. Sullivan described, your concerns with cost--I think at this point in the program we can see the end in sight in terms of R&D [research and development] costs. There are still some risks, and we will tackle those risks. But those aren't going to threaten the program. What we have to do is continue to drive down cost in production, because we still have about 2,800 aircraft to manufacture and that heavy weight in terms of production costs. We have got to go at that from our side in the program to drive the costs down. That bigger issue of affordability has to deal with our budgets. And so where will our budget be--when we are sitting here in April of 2016, where will our budget be? Will we have been sequestered? What will have happened to the top line? You have heard the services testify with regard to the impact of sequestration. If we are sequestered, that will have an impact on this program, and that will then directly have an impact on affordability.
22 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. I appreciate that. My time is up, Mr. Chairman. Maybe we will get that in another member's question. Thank you.
23 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Thank you. Mr. Wenstrup.
24 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412564 |  | Dr. Wenstrup. Thank you, Mr. Chairman. When we went to Eglin, we spent some time with the pilots and asked them what are the problems that they are finding. And, you know, that is certainly the best way to find out, I think, is to actually talk to them. And I know that I think you have been briefed on it and seen the list. And I guess kind of parlaying on what Mr. Walz asked, how many of these things that you see here--and I could go through them all; don't necessarily have to--will we be able to address in the next year? General Bogdan. Over the past 2 years, we have faced a number of technical issues that 2 years ago or a year ago, if you had said, ``Where will you be in April of 2015?'' I would have told you, ``Well, I would like to have this retired and that retired and that retired.'' So let me give you a list of a few of the things that we have retired and now a few of the things we are working on in 2015 when we come back next year will hopefully retire. A year ago there was a lot of speculation and discussion about how good the helmet was going to be, the Generation III helmet, because the Generation II helmet had some shortfalls. It had a jitter problem. It had green glow problems. It had latency problems. It wasn't good enough for the warfighter. Today I can tell you we are flight-testing the Gen III helmet right now and all indications are from the test pilots is that it is much improved, much improved. So I put a half a checkmark in that box and say, ``Okay. We are controlling that.'' Last year we had a major engine problem. I will tell you today we have the solution for that engine problem. It is being put into the field. And by this summer, I will have the final production version of that fix into the production line and that will be behind us. We had a problem with lightning. We were having a problem qualifying the airplane to fly in lightning last year. That problem is basically behind us. And, in fact, I don't know if the guys at Eglin told you, but 2 weeks ago a CF-8 flying--returning from base was struck by lightning. He was in clear air and he was struck by lightning, and absolutely nothing bad happened to the airplane. The pilot landed the airplane. No warnings and cautions. No problems. And we could see where the lightning went into the right wing tip and came out. So lightning is another one we would put on that list of last year a problem, not a problem this year. Fuel dumping was a problem last year because the fuel dump on the airplane comes from the bottom of the wing. And so, when you dump fuel from the bottom of the wing, there is high pressure there. It pushes the fuel up onto the wing and it sticks and it makes the wing wet. We have solved that problem. So those are just a few of the things that a year or two ago were high on our list. What is high on our list this year? We already talked about ALIS. ALIS has a long way to go, sir. It is a complicated 5-million-lines-of-code piece of equipment that we started treating like a piece of support equipment. It is not. It is an integral part of the weapon system. So we have had to take steps in the last 2 years to change fundamentally the way we develop ALIS. We have applied the same techniques we used in developing software on the airplane to now developing software in ALIS. It is just going to take us some time to realize those results. We had a problem with the hook. When we first tested the hook on a C-model a year and a half ago, we missed seven out of eight traps at Lakehurst. We went out to the boat last year and hit 124 out of 124. So I guess what I am expressing here is we are going to have more technical problems on this program. It is a measure of a good program for you to be able to absorb those, find fixes for them, and then continue moving the ball down the field on the program. I think we are in a better position now than we ever have been to address those kind of problems.
25 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412564 |  | Dr. Wenstrup. Well, you are there and you know these things are being addressed. I think it kind of took us a little by surprise, the 80 percent, and it was said kind of casually, like, ``80 percent? Like, that is far from good.'' General Bogdan. Can I make two comments about that just to kind of put it in context? The first thing is--and that is not to mitigate the fact that we know we have a problem there--the jets down at Eglin are the oldest ones we have. They are flying 1B software and 2A software, and they are Lot 3 and 4 airplanes. So they are flying the dogs of the fleet, quite frankly, because many of the newer lots of airplanes have many of the improvements we have learned over the last 2 to 3 years. And the newer software that we are using on the 2B airplanes is going to make that even better. So I can understand the guys down at Eglin feeling like, ``I don't have a very good airplane here after all this time, energy, and money, General Bogdan.'' When it comes to the false reporting, we call those things HRCs, health reporting codes. And on any given sortie, you may get two or three or four of them. What I believe when they are telling you 80 percent is, when you actually get a health reporting code on the airplane and you land, the ones that you get, 80 percent of them turn out to be not good, not that 80 percent of all--every flight you have got problems with the airplane that you don't know about. What we have done is we have gone in and we have started to change the software both in ALIS and the airplane to address that. But at the same time, we now have a history of which health reporting----
26 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. I am sorry to interject here, General Bogdan. I just want to make certain you are not confused, although I think I may be. When they say 80 percent false positives, they mean, out of 100 items where it says there is something wrong with the plane, 80 of them are nothing is wrong with the plane, but they are given a notice that something is wrong and then they have to deal with that notice---- General Bogdan. Correct. Correct
27 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. By the way, Secretary Stackley cringed when you---- General Bogdan. No. You got that right, but here is what I am trying to say. The other important question that they should have told you was each airplane, when it lands, only has about four or five health reporting codes a sortie.
28 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. We saw the list. I mean, the point here being that, if something is telling you 80 percent of the time wrong information, it is suspect. Right? General Bogdan. Yes, sir. And I am going to go check that 80 percent number and get back to you. And it is a problem. We know it is a problem, and we have to address it. [The information referred to can be found in the Appendix on page 95.]
29 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Thank you. With that, Ms. Duckworth.
30 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412533 |  | Ms. Duckworth. Thank you, Mr. Chairman. I find it comforting that--or maybe not so comforting to think that the question I really wanted to talk about was ALIS and it is one that is of concern to the chairman. As a former aviator and, also, a logistics officer, let's talk maintenance and logistics and ALIS. I am concerned that the manpower it takes to clear every single one of those false positives--false negatives is driving up maintenance costs and now you have got more and more man-hours or person-hours or airmen-hours or contractor-hours that have to clear every single one of those. In addition, whether it is 80 percent or whatever it is, I would like to know--and you don't have to give it to me today because I doubt, General, that you have it--how often are you getting a circle red X or a red X status on aircraft that is driving down the aircraft availability for missions and for different mission profiles? Because now, even if it is a false positive, you are affecting mission readiness for the aircraft. And you talked about problems with the system in the past, not necessarily ALIS, but problems that have been fixed, last year the helmets--Generation II and Generation III helmets. Is there a timeline in place to fix all of these problems with ALIS? Do you have benchmarks in place: ``In 6 months you will have X number of lines of codes fixed and within a year we will be at this point''? And then the final question is--one of the issues is not even software. We are talking about the size, bulk, and weight. My understanding is, during the carrier integration phase, ALIS could not deploy and, instead, the USS Hornet [USS Wasp] had to rely upon the ALIS system at Fort Worth, Texas, for logistical support because it was too bulky to deploy onto the [Wasp], which, you know, as someone who flew small aircraft, if you couldn't carry it in the aircraft or sling-loaded under the aircraft, it didn't go with you. The idea that you would have an integral part of your maintenance system that can't even fit on the USS [Wasp] is very, very troubling to me. General Bogdan. Yes, ma'am. Relative to the plan, we absolutely do have a plan for ALIS. As I said before, until about 2 years ago, we weren't treating ALIS much other than a piece of support equipment. We now recognize that it could be its own weapons system. So we have put all the system's engineering discipline, the software metrics--the same kind of things we did for the airplane we are doing for ALIS. So, as an example, this summer the U.S. Marine Corps will declare IOC with a version of ALIS we call 2.01. Today in the field we have Version 1.03. So there is an upgrade program going on. The U.S. Air Force next summer will get 2.02 because we are doing incremental upgrades on ALIS. I will take it for the record that we will show you that integrated and incremental plan to improve ALIS. Relative to the deployability of ALIS, you are spot on, ma'am. Today ALIS sits in a squadron and it is a rack of computers that weighs probably 800 to 1,000 pounds. We recognized a year and a half ago that was not going to work for deploying forces. So today we are redesigning ALIS into what we call a Version 2 deployable version. That will be ready for the Marine Corps this July. It is two-man portable. It comes in about three or four different racks. They take it apart and--two men can put it back together and take it apart. In the future, we will build all of the ALIS system in this deployable configuration and we will get rid of the old 1,000-pound racks we have at the squadrons now. But you are right on, ma'am.
31 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412533 |  | Ms. Duckworth. I would like to make several requests, General. I would like to know what you think will be the point of acceptable for ALIS's performance, 80 percent--whatever you said. I am sorry to be all up your tailpipe in this, but we have gotten to the point where Members of Congress are really concerned. So what are you determining to be acceptable? When will you get there for the software system? You already told me what acceptable is for the size. Right? You said July, two-man portable. And then I would like to know what the maintenance cost has been due to the false positives and how much of that cost will be decreased and what you expect that cost to be in terms of increased manpower hours for both your uniformed personnel as well as for the contractors and all the maintenance that comes about with having to clear every one of those codes. General Bogdan. That is a great set of questions, ma'am. I will take them for the record and we will plan on having that discussion after this hearing. [The information referred to can be found in the Appendix on page 95.]
32 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412533 |  | Ms. Duckworth. Thank you. I yield back, Mr. Chairman.
33 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Ms. McSally.
34 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412611 |  | Ms. McSally. Thank you, Mr. Chairman. Thank you, gentlemen, for your testimony. Dr. Gilmore, in your testimony, you talk about the limitations of the F-35 in close air support. Specifically, you mentioned that the aircraft will need to be under the direct control of a forward air controller using voice communications, there is no ability to use an infrared pointer, there is no ability to have night vision capability--this reminds me of something before the A-10, by the way, not after the A-10--only have 20 to 30 minutes time on station, the current 2B would only have two weapons, but, then, even the follow-on is only going to have 180 bullets even if you are mounting the external gun. And so I am concerned about the capabilities in the close air support, forward air control, and combat search and rescue mission that the F-35 is going to be serving as it replaces aircraft like the A-10. So how many of these shortfalls--and I just mentioned a few of them--will actually be fixed in the 3F? And how many are just inherent, like the 20 minutes time on station and the lack of really total weapons capability? When you think of close air support aircraft like the A-10, it is the survivability, the lethality, which means weapons load, and the loiter time that really make it capable to keep Americans alive. And I am concerned on the second and the third I mentioned, loiter time and lethality as far as weapons load. And, also, are any tests, including survivability--you know, can they take hits like the A-10 can of a SAM [surface-to-air missile] and triple-A [anti-aircraft artillery], small arms, and still be able to fly back? Are you testing those types of things in a low-threat, so to speak, close air support environment, which is what we have been doing the last 25 years?
35 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. With regard to the time on station, the numbers you quoted were for the F-35B, and that was 20 to 30 minutes. Now, you can extend that by refueling with tankers, but then, of course, you have to plan for the tankers. The F-35A would have up to about 45 minutes on station. That compares with about 90 minutes on station for the A-10. And that is something that will--you know, that is a limitation that will persist because of, you know, the engine and other aspects--aerodynamic aspects of the aircraft. With regard to some of the other limitations that are discussed in my testimony, like, for example, the deficiencies in the digital communications, you know, there are problems with the nine-line message. Not all elements of it are accurate at this point. It doesn't work correctly. And so it will require some voice communications if you are performing CAS [close air support], if you are trying to do that with a Block 2B aircraft, and--you know, as opposed to the--you know, the digital nine-line that you can use in the A-10, the Harrier, and the F-16. Those problems are, you know, planned to be corrected in Block 3F.
36 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412611 |  | Ms. McSally. Okay.
37 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. Block 3F will provide additional weapons loads and mixed weapons loads as well as external weapons. So the weapons load will increase in Block 3F. Some of the other problems that, you know, will probably--if you are using a Block 2B aircraft, would require greater coordination with a forward air controller will, based on what the program hopes to achieve in Block 3F, you know, be fixed. And, in fact, if everything that is realized in Block 3F is realized, I think it would be safe to say that you will have much better situational awareness in a F-35 than you would in an A-10, again, if all these Block 3F capabilities are realized, but the Block 2B capability is going to be limited.
38 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412611 |  | Ms. McSally. Great. And the survivability piece, I mean, are you----
39 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. We are----
40 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412611 |  | Ms. McSally [continuing]. Evaluating its ability to take small arms, triple-A, SAM hits and still be able to fly back?
41 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. Yes. My annual report describes some of the testing that has been done, you know, testing against hits by certain kinds of weapons that, you know, could be employed against the aircraft if it were flying low as well as if we are engaged in air-to-air combat. The aircraft has some vulnerabilities that you would have to expect a high-performance aircraft to have. And the A-10 is going to be able to--you know, can take hits that an F-35 couldn't take. But I don't think that the plan for having the F-35 conduct CAS is equivalent in all operational aspects to the way the A-10 would conduct CAS, and the plan would probably be for the F-35 to stand off more from many of these threats that the A-10 does not stand off from. So, you know, the survivability of the F-35 against some of these threats isn't going to be as good as the A-10, but I think the operators would say that they wouldn't use the F-35 the same way they would use the A-10 to do close air support.
42 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412611 |  | Ms. McSally. And thank you. My time is expired. But I will share, as a former A-10 pilot and squadron commander, there are times and there will still be times in the future when you must get down and dirty with the guys on the ground, who are often on the run, unable to give you their coordinates, and you have to visually be able to see where are the good guys and the bad guys. And so you cannot stand off in all CAS scenarios even in the future, and that is a concern I have with the limited capabilities in replacing the A-10. But my time's expired.
43 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. And I agree with you, Congresswoman.
44 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412611 |  | Ms. McSally. Thank you. Thank you, Mr. Chairman.
45 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Turning to Joe Wilson.
46 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400433 |  | Mr. Wilson. Thank you, Mr. Chairman. And, Dr. Gilmore, tomorrow we are having a full committee hearing on the risk of losing military technology superiority and its implication for U.S. policy, strategy, and posture in the Asia-Pacific. What is your opinion of the continued development and production of the F-35 program as critical to our military in maintaining its technological superiority?
47 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. That is for me?
48 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400433 |  | Mr. Wilson. Yes.
49 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. I have stated previously--in fact, the last time I testified on Joint Strike Fighter was before the Appropriations Subcommittee on Defense in the Senate--that the Department has no choice but to make the F-35 work. It is critical to the future of tactical combat aviation in the Department and in the United States. And as far as I can tell and, as Mr. Stackley and General Bogdan have indicated, they and the Department are committed to making it work. However, as has also been mentioned by the chairman and others, this is an extremely complex undertaking. And I think the best way to characterize what is happening here is that the best projections that excellent program managers like General Bogdan make can be undone by the complexity and the unknowns that we continue to face. And so we can expect those kinds of unknowns to continue to arise and to have to deal with them. And so it is going to, in my judgment--and I don't regard this as a horribly profound observation--it is going to take longer to get this job done than anybody--and cost more than anybody now projects, but it is an important job to do.
50 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400433 |  | Mr. Wilson. Well, thank you very much for your clarity. And, General Bogdan, the F-35 is the only fifth-generation aircraft in production today. Please highlight for us what the F-35 fifth-generation capabilities will bring to the fight. General Bogdan. Congressman, the essence of the F-35 and what it can do for us and our allies now and in the future is a combination of different characteristics about the airplane, one of them being stealth, meaning, although not impossible to detect, very, very, very difficult to detect. And once you detect an airplane, you have to go through the kill chain to shoot it out of the sky, and this airplane, with its combination of stealth, electronic attack, electronic warfare capabilities, and its sensors, is very, very good at knocking pieces of that kill chain out. So it is a very survivable airplane in the most heavily defended, complex target environments where we wouldn't otherwise be able to bring other legacy airplanes. So it does that. The second thing it does is its combination of sensors, when working properly and fused properly, provides a picture of the battlespace that is unprecedented for our pilots today. And the ability to see the battlespace in that clarity and to take that picture and send it off board to other airplanes and other platforms is a valuable, valuable tool. So the combination of the F-35 being able to go where no other airplanes can go and its ability to see the battlespace in that kind of clarity creates an advantage for the United States that is critical in future air dominance.
51 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400433 |  | Mr. Wilson. And, again, thank you for your clarity on that. And, Secretary Stackley, I previously represented Marine Corps Air Station Beaufort, and they have just been--the community is so supportive and so enthusiastic about F-35Bs being located there. They are located. What is the current status of deployment there? And what is the future?
52 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Secretary Stackley. Yes, sir. Thanks for the question. Right now at Beaufort I think we have about a dozen aircraft on site. It will be a training command near term, long term. That dozen or so aircraft will build up to a total of 50 across 2 squadrons, and you will see the Marine Corps training there. In the near term, you will see our partners--the U.K., Italy--training there, and that will be a long-term presence just like it is today for Marine Corps aviation training with this program. It is a critical part of the future of the Marine Corps here.
53 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400433 |  | Mr. Wilson. Well, I always like to point out that Beaufort has the right meteorological conditions, and that is very good weather, temperate, and very warm people. So thank you very much.
54 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Mr. Knight.
55 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412614 |  | Mr. Knight. Thank you, Mr. Chair. And I will just make a couple comments. I appreciate you changing the flight pattern for the Joint Strike Fighter because now it gets to fly over my house about 10 times a week, and I love the sound of freedom, and it is always nice to see that. I will remind the members that the F-16, our last multi-role fighter, went through about 138 versions and probably 15 or 16 blocks. So they call it ``test flight'' for a reason. It is not proven flight. It is test flight. We are going into a new generation. It is a new technology. It is a new way for the warfighter to be further into the battle, further undetected into the battle. And so the F-35 is something new for the warfighter. Those are all the nice things I am going to say. But I am going to piggyback on Congressman Walz. I am a freshman. And in a year I am sure I am going to be sitting here and we are going to be talking about the F-35. And the F-35 is a program that is talked about in every one of our districts. Whether we have a base, whether we have an aircraft, it is talked about in every one of our districts. So not just hitting the test points, but being able to go past the test points and get on to the next issue that maybe a test program is having, and the faster that we can get on to a program that they see our Marines flying, that they see the Navy flying and, of course, our airmen flying is the best factor that we can talk about. So in a year, I am going to have great things to talk about the F-35, but I am hoping that we are going to have a lot of these points that the general said--that we are going to be knocking out and moving on. And then my last, last thing is our international partners. You don't have a great multi-role fighter in America without international partners and a good sale program to our international partners. That might be 40, that might be 45, percent. But that is one of the best and most motivating factors for any multi-role fighter, whether it be our F-16 or back to our F-4. So those are all the nice things I will say about the F-35. And I know it is hitting a lot of the test points. I talk to the pilots and the mechanics at Edwards probably on a weekly basis. And it is moving very quickly, and these last 6 months have been very, very good for the program. Thank you, Mr. Chair.
56 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Ms. Graham.
57 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412620 |  | Ms. Graham. Thank you, Mr. Chairman. Thank you all for being here. Just last month I had the opportunity to go on a congressional delegation trip to Eglin to familiarize myself with the F-35 program, and it was a wonderful opportunity. I was there with Chairman Turner and my fellow Floridian, Congressman Jeff Miller. And we share--our districts are right next to one another. And so we have the ability to share the unique training that is available in the Gulf of Mexico. And so my question goes to Dr. Gilmore, to the training opportunities in the Eglin Gulf training areas, and I am specifically interested in ensuring that the test ranges remain and have the capacity to test our F-35s and other future-generation capabilities. So can you please talk about what the Department has been doing to test F-35s at the Gulf Test Range and, also, the efforts the Department is undertaking to ensure that our ranges, and this range in particular, are upgraded so that they can do the necessary tests on this fighter and future generations of fighters.
58 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. The activities at Eglin have been focused on training with the early blocks of software, which has been noted, until Block 2B, don't provide any combat capabilities. So the training opportunities have been limited not because of any limitations in Eglin's infrastructure or capabilities, but because of what the aircraft up to this point have offered. Now, with Block 2B and beyond, the training opportunities, just because of the capabilities that will be provided, will be greater and there will be greater advantage taken of the capabilities of Eglin to serve as a training range. I think, as you know, most of the flight testing that we have been discussing here both for flight sciences and the aerodynamic performance of the aircraft as well as the performance of the missions systems has been taking place at Edwards Air Force Base. And that continues to be the plan because of certain unique assets that exist out there that are critical to testing the capabilities of this fifth-generation aircraft. And so I would expect that, in the future, Edwards and, you know, the Western Test Range will continue to play a very important role in testing. Some of the weapons testing can be done at Eglin, and I expect that there will be more of that testing that is done in the future as well as training that is done at Eglin. So, you know, there is a mix of kind of testing that is done and there are certain unique aspects out on the Western Test Range that really--that don't exist anywhere else that are the reason that most of that testing has been occurring out there. And, in fact, a large part--not all, but a large part--of the operational testing will take place at Edwards as well.
59 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412620 |  | Ms. Graham. Can you just disclose without entering into any classified areas what is unique about Edwards that is not present at the Eglin test range?
60 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. The things that I am discussing that are unique I would have to discuss with you----
61 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412620 |  | Ms. Graham. Okay.
62 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. [continuing]. In the appropriate venue.
63 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412620 |  | Ms. Graham. I understand.
64 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. So I can't really discuss them in an open----
65 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412620 |  | Ms. Graham. Well, I appreciate that. I would just like to ditto my colleague about how wonderful it is in north Florida. We have nice people, warm weather, and great opportunities to test these incredible air----
66 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. And there will be testing and there can be weapons delivery events that are done there in the future, but there are certain unique aspects to the Western Test and Training Range. They have a test and training----
67 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412620 |  | Ms. Graham. Right.
68 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. [continuing]. Range there, too. But I would be happy to discuss it with you in the appropriate forum.
69 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412620 |  | Ms. Graham. I appreciate that, Doctor. Thank you for your time. Thank you. I yield back the balance of my time. Thank you.
70 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Mr. Jones.
71 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400209 |  | Mr. Jones. Mr. Chairman, thank you very much. I wanted to be here for this hearing, and I am sorry I had to leave. But, obviously, Cherry Point Marine Air Station is in my district, and as somebody said earlier, the F-35 is of great importance to many of us around the country. This was an article in Business Insider on March 27th of this year, ``The Marine Corps want[ing] to put flawed new fighter jets into service is the biggest F-35 story right now.'' You have touched on some of this. But I have spent 13 years of my life finding out more about the V-22 than I ever thought I would learn about anything. I was here at the time that the Marine Corps came forward, Commandant Jim Jones, saying that, ``We have got to have the V-22. The V-22 is going to replace the helicopters, heelicopters, from the Vietnam war, and we have got to have it.'' I saw at that point what I was hoping--and no this is not talking about you--but the fact that the Marine Corps was so desperate to get the V-22 that a lot of decisions were made like not fulfilling the testing of the vortex ring state and how that would impact the V-22. They scrapped that testing to save $50 million. The plane that crashed that I have gotten involved in was the crash on April the 8th in Marana, Arizona, where 19 marines were burned to death--the co-pilot's wife lives in my district, Connie Gruber. Her husband was Brooks Gruber. The pilot John Brow's wife, Trish, lives in Steny Hoyer's district--and in trying to get the Marine Corps to write a letter to the wives saying that, ``At the time of this accident, we did not understand the vortex ring state. We didn't know how it would impact in a certain situation. So, therefore, the press release that we sent out the first month of that accident was very misleading, but the press has always picked it up as pilot error.'' Now, what am I trying to get to? What I want to make sure--and I think each one of you have done a great job, what little bit of time I was here today. And I have read many, many articles all around about the V-22, the positive and the negatives. But I hope that, if we are going to put the pilots up and put them into certain situations, that we know the best that we can know, that we are not going to jeopardize their lives, because I have seen the pain with Connie Gruber and Trish Brow that they have carried for 15 years because of misinformation about that accident. And my hope is, with the F-35--and you have done a great job of explaining today, and I know the chairman's been very involved in this--but let's not be so in a hurry to prove that we are right with this F-35 that we would jeopardize any pilot from anywhere. And I want to--with the minute and 30 seconds I have left, I really would like for you to--each one--in a very short period of time tell the American people that we are not going to jeopardize our pilots to prove a point that we have got to have the F-35. General Bogdan. Sir, I will go first. I have been an Air Force pilot for 31 years and have over 3,300 hours in 40 different kinds of airplanes. I would never ever ask a pilot to do anything in the F-35 that I wouldn't do myself.
72 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400209 |  | Mr. Jones. Fair enough. General Bogdan. Safety in this program is our number one priority. I have independent air worthiness authorities that watch what we do. And I would never jeopardize a maintainer or a flier's life just to prove a point about a program. It is not worth it.
73 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400209 |  | Mr. Jones. That is why I respect you. General Bogdan. And I won't do it.
74 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400209 |  | Mr. Jones. I wish that had happened in the year 2000. But I saw the dishonesty at that time to prove a point, and that is why I feel so passionately and strong, and that is why I appreciate you, sir, for what you just said. Thank you.
75 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Secretary Stackley. Sir, I can only echo what General Bogdan had to say. Safety is a top priority on this as well as, frankly, all of our weapons systems developments. We do not compromise on air worthiness. Our standards are high and we do not compromise on those standards. And as far as bringing those standards to bear on this program, we have got our best and brightest working on this.
76 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Mr. Sullivan. Well, I think, you know, speaking as one of the agencies that does oversight on this, I have a lot of confidence in the program manager and the services to be able to deliver a very, very safe aircraft. And I think that this committee is a part of all of that. It is very important. GAO oversight is important. And it maybe was not as good as it should have been back in those days, and that is one thing that--I think this committee, the Congress, and DOT [Department of Transportation] and even GAO are very important to the process.
77 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | N/A |  | Dr. Gilmore. The combat capability of Block 2B aircraft are going to be limited and there are going to be lots of work-arounds that are required for pilots and for the maintainers. And that is already been discussed. So what I am trying to do is--and I know that the program office is trying to do this as well--but what I am trying to do is to make the operators as aware as I can of what they do have and what they won't have. And in Block 2B, unfortunately, there will be--if you ever wanted to use it in combat--and my understanding is, associated with the initial operational capability, the Marines hold out the prospect that they would use it in combat--I will continue to seek to assure that those pilots understand what they don't have as well as what they do have. And in Block 2B there will be a lot of what they don't have.
78 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400209 |  | Mr. Jones. Thank you, sir. Thank you, Chairman.
79 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Mr. Walz.
80 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. Thank you, Mr. Chairman. And I would just do a quick follow-up. And I would like to get on this--and I think I heard my colleague and friend, Mr. Knight. When he talks about test flights, I listen. As we all know, his family holds an important position in American aviation history and test flights. And I think he is right. And I want to get on this issue about we can't expect a perfect product right out of the gate, but there is a question I want to follow up on this June 23rd fire. That was a relatively new aircraft. The way I understand it, it had 160 hours of flight time. It was flown inside its designated flight envelope; so, the pilot wasn't at fault. But despite all this, we had a new aircraft forming at a very easy place where it should have been. We lost the aircraft and nearly lost the pilot. So, General Bogdan, here is my question to you. We have been--the way I understand it, we were informed that the root cause was the F-35 last year was a lack of accuracy in the Pratt & Whitney's model on how the engine would behave under flight conditions on that specific aircraft. Specifically, the model did not apparently account for the rubbing you talked about between certain internal portions of the engine under flight conditions. Here is my questions to you. If that part of the model was not accurate, despite many years and the billions of dollars, what other parts of the engine performance could be inaccurate? And where is that high risk, in your opinion? And, secondly on this, the Marine Corps' version we are going to see later this year, am I correct that it is going to perform lower than what the expectations are? This is a test flight moving to that. So it is at 5.5 g's [force of gravity]. Are you worried that the modeling is not taking into account, when this gets pushed further and further into its flight envelope, what is going to happen, General? General Bogdan. Great question, Congressman. You are precisely right that the original Pratt & Whitney model did not anticipate the amount of heat that would be generated when those two parts of the engine that do rub--and we intended on them rubbing, and they do rub when the airplane's maneuvering--but we did not nearly expect the kind of heat generation we saw because their model, again, failed to capture that. So what we did with the independent air worthiness authorities that work outside of my program office--they put their best and brightest in the Navy and the Air Force on this to get to that root cause. And one of the requirements we had before we ever designed a fix for the engine for that specific problem was to go back and take a look at those models and decide where else was there in terms of risk in those models. And the independent air worthiness authorities at NAVAIR [Naval Air Systems Command] and LCMC [Life Cycle Management Command] had to come and say that they understood where those models were adequate and where they weren't and what Pratt was going to do to improve that before they would even allow us to put the fix on the airplane to get back in the air.
81 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. Were there improvements made to their model? Did you find things that---- General Bogdan. Oh, yes, sir. There were a number of improvements, not the least of which was we looked at all the materials--all the material properties in the engine and revalidated whether the characteristics of those properties, in terms of heating and friction, were accurate and appropriate for what we knew to be the case. Additionally, a fighter engine moves. It moves this way. It moves this way. And it moves this way. We had to make sure that that model, which was describing how much the touching and rubbing would occur, was accurate, also, before we put those airplanes back in flight. That was part of the reason why the planes were grounded for as long as they were.
82 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. So later this summer, when they go and they push that to 5.5 g's and they start pushing ahead of that, you are, I'm certain, as you said--and I know this to be the case--you are not going to put one of those---- General Bogdan. Sure. We took the fix from--the interim fix from that engine mishap and we flight-tested it at Edwards on both engine variants and we took it up to the maximum g limit of the airplane, which is greater than what the Marine Corps is going to be allowed to do this summer.
83 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. And, in this case, we didn't have a loss of life. So is it your assessment this is what test flights do? We learned a lot from this, we are better off, and it---- General Bogdan. What I would tell you, sir, is no surprise discovery is good. But if you are going to have them, it is better to have them on the ground and it is better to have them early in a program before you have had thousands of engines out there.
84 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. Okay. General Bogdan. So, from that perspective, we are okay. And I am just--we are just blessed that that pilot is okay.
85 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 412214 |  | Mr. Walz. Great. I yield back, Mr. Chairman. Thank you for the additional time.
86 | Tactical Air and Land Forces Subcommittee | HSAS-25 | CHRG-114hhrg94746.txt | 35 JOINT STRIKE FIGHTER PROGRAM AND THE FISCAL YEAR 2016...' | 400411 |  | Mr. Turner. Thank you, gentlemen. Thank you for your attention to this very important program. We know that you all have important responsibilities. And thank you for continuing to keep this committee informed as we look to trying to assist in the overall process. With that, we will be adjourned.