## Sheet1
| committee_name | committee_code | file_name | title | govtrack | ranking | speaker_last | speaker_first | speech
0 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. The Subommittee on Space will come to order. Without objection, the Chair is authorized to declare recesses of the Subcommittee at any time. Good morning. Welcome to today's hearing titled The International Space Station: Addressing Operational Challenges. In front of you are packets containing the written testimony, biographies, and Truth in Testimony disclosures for today's witnesses. I recognize myself for five minutes for an opening statement. Good morning. I'd like to welcome everyone to our hearing today, and I want to thank our witnesses for taking time to appear before our Committee. Since 2013, the ISS program has experienced a number of challenges. As a can-do nation, America has always been committed to identifying challenges, addressing them, and advancing to reach out and reach our goal and destiny. We have that same commitment with the ISS. During this time, astronauts have experienced water leaks in their suits three times, with one incident occurring during a spacewalk. On April the 26th, 2013, an unmanned Russian Progress cargo vehicle damaged a laser radar reflector when docking with the ISS. On January the 14th, 2015, a false alarm of an ammonia leak caused the crew to retreat into the Russian segment. On October 28th, 2014, an Orbital Sciences unmanned cargo launch failed just after launch. On April the 28th, 2015, a separate Russian Progress cargo vehicle failed to reach the ISS. On June the 7th, 2015, a planned re-boost of the ISS using a docked Progress vehicle failed but eventually was successful after troubleshooting. On June the 10th, 2015, a visiting Soyuz vehicle unexpectedly fired its engines without being commanded. Most recently, on June the 28th, 2015, a SpaceX unmanned cargo launch failed as well. All of these incidents highlight the challenges of operating in space, and they remind us that NASA's contractors, engineers, and astronauts must be ever vigilant. These events have challenged ISS operations, but the fact that the program was able to effectively respond to these set-backs is a testament to NASA, the ISS partners, and the contractors. We do not know the root causes of some of the accidents yet, but once we have more information, we will be better suited to review those individual events. In the meantime, this hearing allows us to evaluate the operational status of the ISS, review efforts to utilize the unique asset, and assess the prospects for future operations. The ISS is one of the most complex and expensive man-made objects ever built. The American taxpayers currently invest approximately $3 billion dollars per year in this laboratory. We must ensure that every dollar is spent effectively and efficiently. The ISS offers a unique microgravity environment for scientists and engineers to utilize. NASA recently released its Benefits to Humanity publication this week detailing the many benefits that ISS provides back to our lives here on Earth. From advances in our understanding of human health and performance to our use of new materials to the utilization of robotics and satellites, the benefits we receive from ISS are many and diverse and remarkable. In addition to the benefits here on Earth the ISS offers the conditions necessary to prepare and develop critical technologies for deep space and long-duration human spaceflight missions. Successive NASA authorizations direct the administration to utilize the ISS for this purpose. The Human Research Program and Advanced Exploration Systems Program at NASA are on the cutting edge of developing the systems we need to send humans ever deeper into the Solar System than ever before. Right now, Captain Scott Kelly is on day 104 of his year-long mission to study the effects of long-duration human spaceflight. In addition to the utilization efforts of NASA's research programs, the NASA Authorization Act of 2005 designated part of the ISS as a National Lab and the NASA Authorization Act of 2010 directed the administration to sign a cooperative agreement with a non-profit to manage it. NASA selected the Center for the Advancement of Science in Space, or CASIS, to lead this effort. The Government Accountability Office noted in a recent report that CASIS had made great strides in fulfilling the mandate under the law but that more work needed to be done to ensure that measurable progress was being made in a quantifiable manner. I hope to hear from NASA today that the agency is making progress towards answering this recommendation from GAO. As we keep an eye on the present operation and utilization of the ISS, we must also look to the future. Last year the administration announced support for the extension of the ISS program from 2020 to 2024. At present, federal law limits the life of the ISS to 2020. Absent action from Congress to extend it, the administration would be required to begin closeout of the program. There are many questions about the request for this extension. The bipartisan, House-passed NASA Authorization Act of 2015 requires the administration to provide a report to Congress on efforts by the administration to utilize the ISS and how to quantify benefits back to the nation for the required investment for this extension. It also requires the Administration to develop a government-wide utilization plan for the ISS to ensure that every minute the facility is in orbit we are doing what we can to get the most out of it. These reports are critical for Congress to understand the issues that inform whether to extend the ISS. This Committee has a responsibility to ensure that the American taxpayers are getting all that they can from every dollar they send to the federal government. I believe this investment is worthwhile and that the benefits far outweigh the cost. Support for the ISS and its operations and utilization is not a partisan issue. It is an American issue, and I look forward to working with my friends on the other side of the aisle and our partners in the space industry to understand how we can all meet the operational challenges facing the ISS program.
1 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. I now recognize the Ranking Member, the gentlelady from Maryland for an opening statement.
2 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412263 | Ranking Member | Edwards | Donna | Ms. Edwards. Thank you very much, Mr. Chairman, and good morning. Welcome to our distinguished panel of witnesses. I appreciate holding this hearing now, The International Space Station: Addressing Operational Challenges, and as I listened to the Chairman, I'm reminded that the challenges that NASA faces and the agency faces in operating the International Space Station, I would be more concerned if we weren't able to overcome some of those challenges, and I think it's a credit to the crew and the partners that that is true. About a year ago, I and the members of our Committee sat in this room, looked on the screen there, and had the opportunity to communicate with our NASA crew that was aboard the International Space Station, including NASA astronaut Rick Wiseman who's from Maryland. I would note that I promised him crab cakes, and unfortunately one of those accidents that the Chairman referred to destroyed my crab cake delivery. But Rick Wiseman visited with me in my office just a couple of weeks ago and we made okay on that. What happens when you connect real-time with our astronauts who are living, working, and carrying out research in this amazing laboratory that's orbiting 250 miles above us every 90 minutes is really quite an inspiration. Thanks to NASA, the crews aboard the ISS, and so many school children have also had the opportunity to ask questions and learn about human spaceflight through similar downlink events that we experienced here in this room. Yet, in the thrill of seeing and hearing those who inhabit our on-orbit laboratory, we can sometimes forget just how difficult, demanding, and risky it is to maintain and operate the International Space Station, because sometimes we think it's just ordinary, and it turns out that it's rather extraordinary. Orbital debris, malfunctions to key systems both internal and external to the ISS, and human health hazards pose significant risks to the ISS facility and its crew. The unfortunate loss of the SpaceX-7 cargo resupply mission less than two weeks ago, along with the earlier losses of the Russian Progress and Orbital ATK cargo missions over the past eight months, are again stark reminders of the risks and challenges that NASA and its partners have to face. The successful management of these risks for more than 15 years is a testament to NASA and its industry and to international partners. I am confident that SpaceX, Orbital ATK, in collaboration with the FAA and NASA, will identify and resolve the problems that led to the launch failures and will resume cargo resupply to the ISS as soon as it's safe to do so. And in fact, the ISS actually has been resupplied through its partners. Mr. Chairman, we don't have any time to spare. The ISS is a temporary facility. It's currently authorized for operations as you've described through 2020, and given that the operations cost about $3 billion in taxpayer dollars every year, a cost that is actually projected to increase, coupled with the challenges involved in sustaining operations, we really need to ensure that our vision for the ISS is clear and our goals and objectives for using this unique facility are aligned with that vision. I'm pleased that the number of ISS users has actually grown. We've had concerns about that raised here in this Committee. In addition to NASA researchers and NASA-supported academic researchers, the ISS National Laboratory management entity, CASIS, has drawn new commercial users including pharmaceutical companies to the ISS. However, while the range of ISS uses is expanding, the resources to support those activities are not. Funding for the ISS research represents a mere 12 percent of the overall ISS budget. In addition, constraints on cargo transportation to the International Space Station, as well as available power and precious crew time, limit what research can be accomplished at the Station. And in that regard, I know that many of us want to understand the implications of cargo resupply interruptions on planned ISS research, crew operations, and the sustainability of the Station. In addition, Mr. Chairman, there's critical work to be done on the ISS in the areas of human health research and technology development that needs to be carried out if we are going to make progress toward the long-term goal of sending humans to Mars. In January 2014 the Obama Administration proposed to extend ISS operations until at least the year 2024. The Administration has three rationales for the extension: to complete ISS research that supports long-duration human missions beyond low-Earth orbit; to garner societal benefits from ISS research, some of which we see here; and to give NASA and private partners more time to transition to commercial cargo and crew, allowing NASA to focus on human exploration of deep space. Today's hearing provides us the opportunity to examine those rationales in the context of the cost and risks that NASA and its international partners will face in sustaining the ISS for that length of time. So Mr. Chairman, we have a lot to discuss this morning, and I want to thank our witnesses again for being here and with that I yield back.
3 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, Ms. Edwards. I now recognize the Ranking Member of the Full Committee for a statement, the gentlelady from Texas. Ms. Johnson of Texas. Thank you very much, Mr. Chairman, for holding this hearing on the International Space Station. This really is an important topic, and I look forward to the testimony of our panel of witnesses and I welcome them. It is no secret that I have been a long supporter of the ISS. It plays a unique role in furthering research, advancing human spaceflight, and inspiring our young people. Moreover, in addition to being an incredible engineering achievement, it provides a very visible demonstration of the benefits that can be derived from peaceful international cooperation in space. Failures of commercial cargo transportation missions to the ISS remind us that spaceflight is not easy. Failures will occur, and unfortunately these failures will have impacts on the program. We need to better understand those impacts, as well as the plans for dealing with them going forward. And we need to know whether there are any lessons learned that need to be applied to the far more challenging Commercial Crew Transportation Program. I've said before that the ISS is a perishable commodity. We need to be clear on what NASA needs to accomplish with this unique laboratory while it is still operational. While the Administration has proposed to extend ISS operations until 2024, maintaining the ISS involves risk and a significant opportunity cost. We need to ensure that the ISS is being used in a way that maximizes its productivity and value to the nation. In addition, if we are to ensure that the needed ISS research and technology activities are carried out, it is clear that we are going to need to make the necessary investments. Stagnant ISS research budgets do not communicate the message that we are serious about supporting the important research and technology efforts that can only be accomplished on the ISS. That is a problem that Congress could and should fix. Well, Mr. Chairman, we have a lot of issues to discuss today. I welcome our witnesses and look forward to a productive hearing. I thank you, and I yield back.
4 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, Ms. Johnson. If there are Members who wish to submit additional opening statements, your statements will be added to the record at this point. At this time I would like to introduce our witnesses. Bill Gerstenmaier is the Associate Administrator of the Human Exploration and Operations Mission Directorate at NASA. Our second witness today is John Elbon, Vice President and General Manager of Space Exploration for The Boeing Company. Testifying third is the Honorable Paul Martin who has served as NASA's Inspector General since 2009. Our third witness is Shelby Oakley, Acting Director of Acquisition and Sourcing Management for Government Accountability Office, GAO. Today's final witness is Dr. James Pawelczyk, an Associate Professor of Physiology and Kinesiology at the Pennsylvania State University and a retired astronaut. In order to allow time for discussion, please limit your testimony to five minutes. Your entire written statement will be made part of the record. I now recognize Mr. Gerstenmaier for five minutes to present his testimony.
5 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Thank you, Mr. Chairman, and thank you for the opportunity to testify on behalf of myself and the men and women that work on the International Space Station. This is one of the most talented and dedicated international teams in the world. The ISS is an amazing research facility. Today on the ISS during this expedition, there are 329 research investigations in progress. These span topics from human research into how the human body performs in microgravity, basic biology, and biotechnology, physical science, Earth and space science, technology development, and education. There's never been this scope of research performed on a continuous basis in space. We are also in the midst of a one-year crew expedition. This mission will give us detailed information into the human adaptation to the space environment with mission durations approximately equal to the Mars transit time. We will also get a unique chance through the twins study to see how the human genome changes when exposed to microgravity. We have kept a continual crew presence on the ISS for almost 15 years. Eighty-three countries from around the world have used the ISS for research. Further, private companies through the National Laboratory and the Center for the Advancement of Science and Space have used the ISS. This week in Boston there was an ISS users conference. This is an exciting time as many new researchers are beginning to see the advantages of space-based research to augment their terrestrial investigations. The growth of non-NASA research is exciting and shows that there's a generic interest in using the unique properties of space to investigate basic research opportunities typically only done on the Earth. Space provides a unique window into any physical process that is affected by gravity. Further, the human body reacts in space with many conditions that mimic conditions facing the elderly: bone loss, muscle wasting, immune system degradation, and balance problems. Using animal models, unique insight, and potential new treatments for the elderly can be developed based on Space Station research. As the Chairman stated earlier, operating under frontier of space is not easy. In the past nine months, three independent cargo vehicles were lost on the way to the ISS. This graphically shows the difficulty of living and operating in space. The lost vehicles have different designs, different heritages, different manufacturing, different build processes, and utilize different ascent trajectories. The failure of these three systems shows the difficulty of launching and operating in space. We often think that ISS is only 250 miles away and that the journey is easy. This is not true. We are essentially operating these systems at the edge of our engineering capability. We also often think that if only we provide more insight and oversight, we can lower the risk of cargo delivery. Unfortunately, the demands required to escape Earth's gravity expose us to the same level of risk no matter how much insight we add. But the insight can give us insight and help us understand the designs to make sure that we can end up with better designs. The right level of insight can reduce and find design errors. However, too much insight can distract the teams from working on and improving design. It's amazing that even after these three failures, the basic ISS operations were not impacted. This is attributed to the teams that manage and operate the ISS. They learned and are implementing the hard lessons from the Columbia tragedy where the ISS had to operate without the shuttle for several years. The consumables management processes and logistics resupply techniques learned are proving their worth. However, these failures are not without consequences. Several of the agency performance goals associated with research and cargo flights will not be met. The ISS program is reducing consumables margins on ISS to favor research. This will not be enough to recover the research impacts. The delay in the Soyuz crew flight, which was required to allow the teams to understand the Progress failure, required the ISS to operate with three crew for approximately three weeks longer than planned and will impact research crew hours. The impact of the loss also had real implications to students and researchers who lost cargo on the Orbital ATK-Cygnus flight only to lose the replacement and return-to-flight hardware again on the SpaceX flight. They suffered a double loss. The loss of the international docking adapter can be accommodated schedule-wise without impacting the crew program but will result in a dollar loss to ISS. ISS is a phenomenal resource for the nation. The research being done on ISS can be done no place else. ISS can serve as an innovation accelerator for private entrepreneurs, help NASA prepare for journeys beyond low-Earth orbit, and benefits directly people on the Earth. Congressional support for ISS operations through at least 2024 would be a positive sign to the international partners and future users of ISS. Operating on the frontier is not easy, and we need to not get complacent and think ISS operations are routine or easy. They are not. The ISS team has done a great job of managing in a technically demanding environment. The ISS team will continue to look for ways to improve. The ISS teams need to be given flexibility to manage, and others need to understand the benefits of dissimilar redundancy and how it can be used to provide robustness. The benefits of ISS will take longer to be realized than most can envision, but the benefits of ISS will exceed the expectations of all involved. I would also like to thank the Committee for their support to human spaceflight, especially the authorization activity associated with Commercial Crew, SLS, Orion, and ISS. I look forward to your questions. Thank you.
6 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Yes, sir. Thank you, Mr. Gerstenmaier. I'll now recognize Mr. Elbon for five minutes to present his testimony.
7 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Elbon |  | Mr. Elbon. Chairman Babin, Ranking Member Edwards, and Members of the Subcommittee, on behalf of The Boeing Company, thank you for the opportunity to testify today to provide an update on Boeing's role in the International Space Station. And Mr. Chairman, as one of your constituents, congratulations on your selection to lead this important Committee. Boeing is extremely proud to have supported NASA in the design, integration and assembly of the ISS. As NASA's prime contractor, Boeing delivered the U.S. elements of the ISS and provided system integration for the stage-by-stage assembly on orbit of all U.S. and international elements. We continue in the ISS sustainment role today. On November 2, the world will celebrate 15 years of continuous presence in space, human presence in space, with international crews living and working aboard the ISS. At a time when many decry a gap in America's space program as we transition from the Space Shuttle to commercial transportation, we who know ISS know that America and our partner nations are making advances in space every day. The International Space Station has been recognized as the largest, most complex international scientific and engineering project in history and the world's largest endeavor in space to date. Ongoing improvements are making ISS even better. The Station brought together hardware and software from 16 countries around the globe and 37 states and more than 10,000 suppliers in our country. About the size of an American football field, the ISS is larger than a six bedroom house and has the internal pressurized volume of a 747. ISS is an engineering marvel, a beacon for international cooperation, and a shining example of what can be achieved through strong leadership and unity of purpose on behalf of humankind. As NASA's contractor for sustaining engineering of the ISS, Boeing is responsible for maintaining the Station and ensuring the full availability of the unique research laboratory for NASA, international partners, other U.S. Government agencies and private companies. In performing this role, we continue to work with NASA to reduce the costs of sustaining the International Space Station. Over the past ten years, we have reduced the cost of our sustainment role by more than 30 percent. These savings has enabled NASA to fund ISS improvements such as the NASA Docking System, the critical component supporting the increase in the number of commercial vehicles visiting the Station. These improvements help to keep ISS at peak efficiency today and provide a basis for continuing strong performance well into the future. With NASA, we recently completed a technical assessment of the useable life of major ISS hardware components. Our study indicates that the Station will be operable at least through 2028. Long-term viability of the Station is an important factor in continuing to attract researchers, who invest considerable time in preparing their experiments for operation in space. The continuing on-orbit reliability of ISS and the improvements made to further enhance research capabilities are a boon to maximizing facility utilization. Our work on ISS enables many benefits and improvements both to enable continuing human space exploration and to improve the quality of life here on Earth. ISS continues to be used for developing multiple technologies to support deep space exploration. NASA is developing highly reliable life support systems to address needs for future exploration habitation systems. The ISS is a test bed for learning how the body reacts to prolonged weightlessness and allows us to develop countermeasures now. And we are learning self-sustainment skills, such as growing food in space and recycling water. All of these things are important to learn and understand before we explore farther into our solar system. Research on ISS has led to numerous improvements on Earth, from the medical field, to Earth observations, to providing clean water in underdeveloped countries, to how we diagnose and treat patients in remote areas. Over the past several years, I've had opportunity to interact with leaders in countries that are not engaged in the ISS or do not have a space program. Without exception, in every one of these conversations about space exploration, these leaders express a strong desire to be involved in space, and more specifically, the International Space Station. They see the value of ISS: to inspire their youth to pursue STEM education, to create economy-expanding high technology industries, and to provide a significant source of national pride. This fresh perspective from leaders outside Station international partnership recognizing the tremendous value of ISS serves as a strong reminder to U.S. leaders and to all who are charged with the care of this national asset and global resource. We must never take what we have in ISS for granted. We must ensure that the International Space Station is well-funded, meticulously maintained and operated, and fully utilized for meaningful, high-value research. Thank you, and I look forward to your questions.
8 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, Mr. Elbon. I now recognize Mr. Martin for five minutes to present his testimony.
9 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Martin |  | Mr. Martin. Thank you for inviting us to be part of the discussion about NASA's challenges in operating and maximizing research on the International Space Station, a very timely topic in light of the loss of three cargo supply flights over the past eight months. The Office of Inspector General has issued four reports related to the topic of today's hearing during the past two years, including reviews that examine NASA's plans to extend Station operations until 2024 and its contracts with private companies to fly cargo and eventually crew to Station. We have five more reviews related to this topic under way, including an examination of October's cargo resupply failure, NASA's efforts to manage health and behavioral risk for extended space exploration, and challenges to international cooperation in space. Our audit from last September of NASA's plans to extend the ISS reported that the agency had identified no major obstacles to continued operations through 2024. However, we found NASA must address a series of technical challenges, including ensuring adequate power generation in light of degradation of the Station's solar arrays as well as a limited ability to transport large replacement parts to Station. While NASA officials estimate an annual ISS budget of between $3 and $4 billion through 2024, we anticipate the cost may be higher. First, much of the projected increase is attributable to higher transportation costs, and we found NASA's estimates for cargo and crew transportation optimistic. Second, most of the agency's international partners have yet to commit to Station operations beyond 2020, and a decision by one or more not to participate could drive up costs for NASA. As noted in our report, the number one operational risk for the ISS program is ensuring the ability to deliver supplies and astronauts to Station. While NASA is working with two commercial cargo providers for redundancy, flights by Orbital and SpaceX are now on hold pending the outcome of accident investigations and approvals from the FAA and NASA. In addition to the loss of important supplies, the failed cargo flights have affected NASA research aboard Station in at least three ways: number one, by reducing available crew time due to a temporary delay in returning the Station's crew complement to six astronauts; number two, by increasing cost to replace the lost research; and number three, by delaying return of experiments due to the suspension of flights by SpaceX, the only company capable of bringing cargo back to Earth. Because NASA uses the ISS as a research platform to study a variety of risks associated with human travel and long-term habitation in space, it is an important part of its plans to send humans beyond low-Earth orbit. As we have reported in the past, utilization of the ISS for research has increased over the years, but several factors continue to limit its full potential. For example, until a seventh astronaut is brought aboard the Station, NASA will not be in a position to maximize crew time devoted to research. In addition, on-board crew will soon devote substantial time to reconfiguring the ISS to accommodate the commercial vehicles NASA hopes will transport astronauts beginning in 2017. To that point, late last year, NASA awarded $6.8 billion in contracts to Boeing and SpaceX to complete development of their spaceflight systems for crew. But NASA's Commercial Crew Program faces several significant hurdles, including unstable funding, the need to provide timely requirements and certification guidance to contractors, and coordination issues with other federal agencies. Given its importance, the OIG recently initiated a follow-up audit to review the status of NASA's Commercial Crew Program. And that concludes my prepared remarks. Thank you, sir.
10 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, Mr. Martin. And I now recognize Ms. Oakley for five minutes to present her testimony.
11 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Oakley |  | Ms. Oakley. Good morning, Chairman Babin, Ranking Member Edwards, and Ranking Member Johnson and Members of the Subcommittee. Thank you for inviting me here today to discuss GAO's work on NASA's management of the International Space Station. As you know, the United States has spent tens of billions of dollars to develop, assemble, and operate the Space Station over the last two decades. The United States could spend billions more in coming years to further capitalize on the investment, given the potential extension of operations to 2024. Today I will discuss three areas: First, NASA's budget for ISS; second, some challenges that could affect increased use of ISS; and finally, steps that NASA and CASIS could take to better document and assess progress in this regard. NASA continues to make a significant investment in ISS each year. This investment is projected to increase over the next five years mainly because the ISS program will begin to fund commercial crew flights. In 2020, transportation costs will be over 55 percent of the projected $4 billion ISS budget. Unlike transportation costs, costs to operate and conduct research on ISS are projected to remain relatively stable through 2020. NASA officials have indicated that the funding priorities for ISS are crew safety and transportation, maintaining the facility, and finally research. As a result, any increases to transportation costs or operations costs could diminish available funding for research. Furthermore, the potential increases to the ISS budget as a result of the planned extension to 2024 are currently unknown. Second, NASA and CASIS face several challenges that could negatively affect their efforts to increase use of ISS for science including cargo transportation failures and delays, limited progress in raising additional funding for research, and increased demand for crew time and facilities. Recent mishaps of the commercial cargo vehicles have had a direct impact on both CASIS and NASA efforts to increase research on ISS. For example, launch failures and delays have already resulted in the loss of CASIS-sponsored research and increased costs by almost $500,000, and let's not forget your crab cakes, Ms. Edwards. Furthermore, additional increases are likely as a result of the most recent failure. For CASIS, absorbing these increases has and could continue to be challenging because it has thus far made limited progress raising additional funds for science from external sources. For example, in 2014, CASIS had only received a little over $9,000 in contributions. However, CASIS has seen an increase in commitments from external donors. Specifically, in 2014, it received commitments of over $12 million. CASIS also faces challenges with competition for available crew time and a heavy demand for key facilities which limits the amount and types of experiments that CASIS can bring to ISS. Crew time is already allocated at or over 100 percent. To address this challenge, NASA and CASIS are dependent on commercial crew providers delivering promised capabilities as planned in 2017. With these capabilities, NASA will be able to add a crew member to ISS who will devote most of his or her time to research, effectively doubling research time. However, many technical challenges and NASA's ability to fund the Commercial Crew Program could delay these efforts. Finally, even if NASA and CASIS can effectively navigate these challenges, demonstrating a return on investment is very difficult in scientific research and can oftentimes take many years. In the short term, it is essential that CASIS continues to make progress promoting research and achieving its goal of increased use of ISS. We reported in April that NASA and CASIS could do more to objectively define, assess, and report on such progress, for example, by assigning measurable targets or goals to its annual performance metrics. NASA and CASIS concurred and agreed to take action in response. In conclusion, potential extension of ISS to 2024 will likely require significant continued investments. As a result, ensuring that ISS capabilities are being used to support significant scientific gains is critical. Furthermore, demonstrating and communicating the return on investment could help support NASA and CASIS in achieving their shared goal of developing sustained commercial markets in low-Earth orbit. Chairman Babin, Ranking Member Edwards, and Members of the Subcommittee, this concludes my prepared remarks. I'm happy to take any questions that you have.
12 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, Ms. Oakley. Now I'd like to recognize Dr. Pawelczyk for five minutes to present his testimony.
13 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Pawelczyk |  | Dr. Pawelczyk. Thank you, Mr. Chairman, Members of the Subcommittee, good morning to you. I thank you for the opportunity to discuss the status of research using the International Space Station. It's the only platform of its kind, and it is absolutely essential to NASA's exploration goals. To prepare for this hearing, you asked four specific questions, and I would like to briefly address each in the time allotted. You asked about opportunities and challenges. Well, the Augustine Commission emphasized three unique stressors that future astronauts will face: prolonged exposure to solar and galactic radiation; prolonged periods of exposure to microgravity; and confinement in close, relatively austere quarters. All of these stressors are present in the ISS environment. Martian operations add more stressors: a dusty, dim, environment and a gravitational field that is a little more than a third of our own. Unless we improve our centrifuge capabilities on the ISS--they are limited at the moment--we risk sending humans to Mars with little or no knowledge of how mammalian biology responds over years in a gravitational field less than Earth's. Two challenges dominate the landscape, limited crew time and limited access to the ISS. We can reasonably anticipate that competition for time will become worse as the facility ages and demands to perform necessary maintenance become more acute. Access is really a matter of competing programs. CASIS-sponsored research and peer-reviewed NASA-sponsored research vie for scarce resources. Better coordination between the two entities is needed. You asked about critical areas of research. The National Research Council's Life and Physical Sciences Decadal Survey, which was completed in 2011 at Congress' request, summarized and sequenced 65 high-priority research tasks. Furthermore, the decadal study created two notional research plans, one with a goal of rebuilding a research enterprise and the other with a goal of a human mission to Mars. More about those goals in just a moment. You asked about priorities. Well, prioritizing ISS research isn't a new concept. In fact, we've been working on that problem for close to 15 years. But the key question for prioritization isn't scientific, it's programmatic and it's something like this: Shall discovery research or fundamental research or translational research take precedence in the mature years of the ISS research program? The answer to that question has to be provided by government. Once those programmatic priorities are sequenced, can we prioritize the research? Absolutely. The LPS Decadal Survey provided a very detailed scheme and used eight unique criteria to do so. The process for operations, you were curious about that, is well understood. CASIS receives its 50-percent allocation followed by human research, then technology demonstrations, and what resources remain are devoted to biology, physical sciences, and the Science Mission Directorate. You asked about implications for extension and criteria that Congress should consider. I think one of the first tests that Congress should apply can be answered with a simple yes or no question. Is NASA prepared to operate a robust research program through 2024? And in my opinion, the answer is an unqualified yes, exclamation point. Absolutely. The transformation of this organization in the past five years has been nothing short of remarkable in the life and physical sciences. I've provided seven examples of that in my written testimony. But there are large knowledge gaps for Mars missions that will be one year or longer. The IG recently reported on this topic, and there are four areas where I'd like to see the report go a little bit further. First, the IG found that extension to 2024 wouldn't provide enough time to mitigate 13 human health risks for a Mars mission. I'm not quite prepared to accept that conclusion. There's simply too many degrees of freedom to establish useful risk criteria at this point in time. These risks need the context provided by a thorough task analysis of future Martian operations. Second, the report didn't address powered down mass to any great extent, and we may need powered sample return for additional research tasks. Third, the IG emphasized average crew time as a metric to quantify research utility. It's a good metric, but I'm not sure it goes far enough. I think we need to work on the concept of efficiency and evaluate and improve the efficiency of the research time we have. And finally, the IG noted that research time is constrained with a six-person crew. We need that seventh member. So my top recommendations are the following: Prioritize the programmatic goals, review the essential resources for extended mammalian research, including that seventh crew member, a scientist astronaut whose nominal responsibility is research, and finally to extend biological experiments to cover a substantial portion of mammalian life cycle and incorporate Martian gravity equivalents wherever possible. Given those sufficient resources, I am very optimistic that NASA can deliver another decade of rigorous translational research. I sincerely thank you for your support of the program and the opportunity to appear.
14 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, Dr. Pawelczyk. I thank the witnesses, all the witnesses, for your testimony. Members are reminded that committee rules limit questioning to five minutes. The Chair now recognizes himself for five minutes. This question will be for Mr. Gerstenmaier and Mr. Elbon. The SpaceX mission had a new commercial crew docking mechanism, water filtration device, and a new spacesuit on board. Can you explain the impact of the loss of these items on the ISS and Commercial Crew Programs? And how do you plan to mitigate these impacts? Mr. Gerstenmaier?
15 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Okay. We'll start with the international docking adaptor that's scheduled for Commercial Crew. It was lost. We wanted to have two units on orbit before we began commercial crew flights. We'll still be able to, I believe we'll be able to, support that schedule. We'll take the parts from a third unit that was being assembled as a spare or a backup and work with the contract to go ahead and extend that and get that delivered on time. The next docking adaptor is scheduled to go in the next several months, and we'll figure out the right cargo flight to take it up. And one docking adaptor will be sufficient to support the Commercial Crew Program. So I think we can accommodate that. The biggest impact to us is the cost associated with now having to manufacture a third unit from the spare parts that remain. On the multi-filtration beds, we think before the Japanese transfer vehicle flies in August, we should be able to get a new transfer bed manufactured again through the outstanding work of the Boeing Corporation to help us expedite that work, and we've got plans in place to do that. We've been trending down on the toxic organic compounds on board Space Station, so we're still in a stable configuration with the beds we have on orbit. We'll continue to monitor that carefully. But we should be okay from that standpoint. The loss of the spacesuit, we will probably now reconfigure one of the spacesuits we had planned on returning on Space Station. We'll do more repairs on it on orbit, and we'll have that space suit available to go do EVAs. And again, we've also put a contract change in place to work with the Orbital Sciences Corporation to look at carrying spacesuits in the future for us. So I think we've mitigated all three of the concerns that you have. The impacts will be not significant, and we can accommodate them but there are impacts with each one of them.
16 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you. Mr. Elbon?
17 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Elbon |  | Mr. Elbon. I'll just add to what Mr. Gerstenmaier said. The most significant involvement from Boeing's perspective is with the docking adapter. The second unit is in Florida and will be ready to fly when we resume flying. And the third unit, the parts are available at our suppliers and in Houston and we're under way putting the plan together to assemble that third unit to replace the one that was lost. As Mr. Gerstenmaier mentioned, we're working very closely with NASA to understand the water filtration issue and to get those components ready to launch on the next resupply vehicles that go up. So I agree that we're in good shape to support the crew on orbit.
18 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Okay. Thank you. Next question. NASA's Aerospace, and this will be for Mr. Gerstenmaier, NASA's Aerospace Safety Advisory Panel has recommended that as NASA assesses ISS life extension, it should also review the objectives for continued ISS use and clearly articulate them to ensure that the costs and safety risks are balanced. Given that human spaceflight is inherently risky, that risk always needs to be weighed against the value to be gained by the endeavor. What are NASA's objectives for extending ISS operations through 2024?
19 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Again, on the human research front, there's many medical investigations we're looking at that were described by other panel members about the radiation environment, the microgravity environment, and we need to understand those and have those risks mitigated and understood before we're ready to commit to longer endeavors in space. And those are all in plans and are in place. We have detailed investigations and the current one-year expedition on board the Space Station is addressing many of those issues and concerns, and that's moving forward.
20 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Okay. Thank you. And then finally, for Mr. Martin, what insight does NASA have into the mishap, investigations being performed by Orbital ATK and SpaceX? Looking back at the Apollo 1 accident, the Challenger accident, and the Columbia accident, do you believe that the investigations have benefitted from an independent review separate from the contractors or the program?
21 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Martin |  | Mr. Martin. Thank you, Mr. Chairman. My understanding is the FAA granted licenses to the private contractors, both SpaceX and Orbital ATK, and under the contract, they are leading the accident investigations. I believe with the Orbital mishap that NASA has a separate review ongoing to try to get to the root cause there. But there is not the same kind of independent accident investigation board if it were a NASA-owned failure. And I think we're currently conducting a review that's going to look at some of the concerns we have about the independence of a contractor-led accident investigation board. But again, pursuant to the contract and the license for the FAA, that's the way it's intended to be.
22 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Okay. Thank you. And that completes my questions. I now recognize the Ranking Member, Ms. Edwards.
23 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412263 | Ranking Member | Edwards | Donna | Ms. Edwards. Thank you, Mr. Chairman, and thank you to the witnesses again. Mr. Martin's report of September 2014 found that NASA's estimate for the ISS budget $3 to $4 billion per year through 2024 is overly optimistic. That was reiterated obviously in your testimony. And so I'm just really curious from Mr. Gerstenmaier, if you could talk to us about the basis of your estimates for projected crew and cargo transportation costs to support ISS. And I would note in that for example, there have been three cargo mishaps in the last eight months. Was that factored into your projections for costs? Because it would seem that that alone would then begin to shoot costs up if those kinds of accidents, which one could expect might happen, over the course of operations over another--to 2024. So it would be helpful to know what your basis for those estimated costs are and respond to the challenges that Mr. Martin has laid out in his September 2014 report.
24 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. We've been looking and working very aggressively to look at cost management and cost control. We've consolidated some contracts into a smaller number of contracts. We also are using competition to attempt to drive down the cost. We're in the process--right now we're in a blackout period of where we're going through a cargo resupply services number two contract award. We've got extremely good competition from that activity, and we believe competition will help us control and hold those costs down. So I think we're actively working. We're aware of those cost issues and the challenges in front of us. The teams have objective acquisition strategies. We have effective consolidation plans, and we're removing costs from the program as we can. And we believe we can hold those costs down, and we can provide some objective evidence of what we've done and seen in past contracts versus future contract entities.
25 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412263 | Ranking Member | Edwards | Donna | Ms. Edwards. And Mr. Martin, I've heard from Mr. Gerstenmaier, but since your 2014 report, would it still be your assessment that NASA's projections are overly optimistic? And in your analysis, would you factor in three, you know, mishaps, failures, in a year in terms of looking at the costs?
26 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Martin |  | Mr. Martin. Yes. I'm not exactly sure whether they factored how many accidents in. But I do think that their cost projections are overly optimistic and continue to be. Over the life of the program, the ISS has shown eight percent increase annually in costs over the life of the program. In fact, from 2011 to 2013, there was a 26 percent cost increase for the ISS. So moving forward, as we go out, as NASA considers extending the life of the Station to 2024, it's projected that in 2024, 59 percent of Station expenses will be for crew and cargo transportation. That's a big piece of the pie.
27 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412263 | Ranking Member | Edwards | Donna | Ms. Edwards. Just curious for all of the panelists, if you look at NASA's rationale for extending to 2024, they include research and technology discoveries that benefit society, enabling human exploration to Mars, establishing crew and cargo to low-Earth orbit, and sustained commercial use of space. Just curious as to whether any of you believe what NASA's top priority should be. I mean, that's a big list in itself, and it's kind of hard to figure out what should be first versus fourth. Dr. Pawelczyk?
28 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Pawelczyk |  | Dr. Pawelczyk. Thank you very much for that question. And it's a great one, and I think it's an extremely important one for this Subcommittee to take on. So the three biggies as you mention them really are this idea of discovery science. What are the big science questions that we want to have answered? We may not recognize the utility of those for a period of years. A piece of research equipment that we flew on my mission in 1998 was largely used in last year's Nobel Prize-winning awards. So that's 16 years to recognize some return on that investment, but it's a very important return nonetheless. There's also translation, this idea of what do we need to do in order to go further. And of course, you mentioned the commercialization aspects. We have contended in the scientific community for many years that it is not our job to sequence those priorities. It is the job of government. It is the job of either the executive branch or the legislative branch, and I'll leave it up to you to sort out which is which. But I believe you've been pretty clear at this point. When I look at the authorization language for this year, you've said Mars is very important, but it's not an either/or. It's an and. NASA will also maintain a fundamental research program. So I think you've already told us that Mars is the answer. And when you look at the research that remains to be done, the risks that sit in the red, most of them, and about half of them, are associated with the extended duration on Mars, so a notional mission of approximately three years duration. I don't know of another research platform that is going to provide us extended research capability to answer those three-year questions. The ISS is our choice for that, and I think that's how it should be used.
29 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412263 | Ranking Member | Edwards | Donna | Ms. Edwards. Thank you. Thank you, Mr. Chairman.
30 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you. And now I'd like to recognize Mr. Brooks.
31 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. Thank you, Mr. Chairman.
32 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Five minutes.
33 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. Yes, sir. Mr. Gerstenmaier, in light of the recent launch failures, is NASA reassessing their insight and oversight approach for the development, production, and operations of commercially provided vehicles that service the International Space Station?
34 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. As part of the accident investigation with the SpaceX event that occurred, part of our Commercial Crew Program representatives are part of that activity with SpaceX. So they are actively involved in analyzing and understanding what occurred on the cargo vehicle with an eye towards any design changes, any process changes, any hardware changes that need to be made in the crew program. So we're actively involved in transitioning that information from this failure directly into the crew program.
35 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. Thank you, and I appreciate that response, an effort on behalf of NASA. In my experience, NASA has a tremendous amount of insight and expertise, and I would encourage NASA to show the leadership that you indicate they are showing and the management skill that you indicate that they are doing to assist with Commercial Crew so that they can be more successful than they have been most recently. This question is with respect to Mr. Elbon and Mr. Gerstenmaier. The loss of the SpaceX vehicle two weeks ago has been described as a big loss. Part of that loss was a replacement spacesuit for the International Space Station. What are the implications to the International Space Station program for the loss of this suit?
36 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. As I described earlier, we'll probably take one of the suits that are on orbit and then refurbish it on orbit instead of returning it to the ground, and then we will develop a capability to transport suits that areon all of our cargo vehicles so that we can bring other suits up to Space Station as needed to support the EVA activity.
37 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. Mr. Elbon, do you have anything to add?
38 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Elbon |  | Mr. Elbon. The space suits themselves are not part of our sustaining contract, so I'm not in the middle of working that. We do however help NASA with all the analysis necessary to figure out which activities need to be done on EVA so that we can make sure that Space Station can continue to operate with the capabilities that exist there.
39 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. What was the cost of that lost spacesuit?
40 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. I don't have a specific cost, and I can take that for the record. We have 13 spacesuits that's available to us. They're from the Shuttle Program, and this was one of those suits. We will not replace that suit. It will just continue to be lost, and it will not be replaced. We have sufficient suits remaining in our inventory to continue to operate safely through the 2024 and beyond timeframe.
41 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. Well, the items that NASA's had on these most recent launches, who is it that is absorbing the cost of those lost items that were being transported to the International Space Station? Is that the commercial crew provider or is that
42 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. For the NASA items, the losses are borne by NASA, and we estimate the NASA cargo loss roughly at about $110 million or so on the SpaceX flight. The researchers, they're responsible for their hardware. They bear the loss from the research hardware that was lost, and that's how that splits out.
43 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. Is there going to be any future effort by NASA inasmuch as we're hiring private contractors to require those private contractors to reimburse NASA for equipment and materials lost because the private contractors were unsuccessful in launching their vehicles?
44 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Our contracts today have a final milestone payment associated with successful delivery of cargo on orbit. Obviously, they will not receive payment for the accomplishment of that milestone, and we're investigating the advantages and disadvantages of having essentially insurance provided for these other capabilities, or to provide for lost cargo in the future. We haven't made a decision yet on whether that is cost-effective for us or not, but we're taking a look at that to see if it's effective to have insurance or it's better that we just essentially indemnify and the users bear the risk of the loss.
45 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. The monies that will be withheld as payment to the private entity spacecraft providers, is that enough to offset the losses that NASA has incurred?
46 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. It offsets a portion but not the entire amount.
47 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. So American taxpayers can rest assured then that at least we'll have some recoupment of the losses that American taxpayers have suffered as a consequence of the private sector providers' failure to provide the represented craft?
48 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Yes.
49 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412395 | Vice Chair | Brooks | Mo | Mr. Brooks. That's all, Mr. Chairman. I yield the remainder of my time.
50 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Yes, sir. Thank you. And I now recognize the Ranking Member from Texas, Ms. Johnson. Is she here? Voice. She left.
51 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Oh, okay. Voice. It's Mr. Bera.
52 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Mr. Bera from California. I'm sorry.
53 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412512 | Member | Bera | Ami | Mr. Bera. Thank you, Mr. Chairman, and I thank the Ranking Member for this hearing. As a child growing up in Southern California in the aerospace industry in the '60s and early '70s, it was remarkable what we could accomplish as Americans when we dreamt big. And when we think about the International Space Station, it really, truly is an engineering marvel, something that over time has, as the witnesses have noted, 15 years of uninterrupted humans living in space. Remarkable. When we think about this and when we think about where we want to go, we have to continue to think big as a nation. We have to not be afraid of thinking and addressing the issues, particularly as we dream about human space travel to Mars. We don't know how we're going to get there, but that should not daunt us and that should not stop us, and that should not stop us from making the investments that allow us to continue to incrementally dream big. Again, that is what we've done throughout our existence as human beings. We've not been afraid to explore. We've not been afraid to ask those questions, and certainly this body has a responsibility to continue to push for the next generation of discovery. That said, we increasingly move to this coordinated role between what the public invests in partnership with commercialization of space. The last few months have been a bit concerning. We've been fortunate that the accidents did not have human beings on there and only cargo. But as we look at this partnership of commercialization and human space travel and taking human beings to the Space Station and beyond, it is a bit worrisome. My question, let me direct it to Mr. Martin. In light of these recent accidents and the investigation of these accidents, could you elaborate and maybe expand on NASA's role in making sure there's a transparent investigation? I mean there is some concern if just the commercial entities are investigating without NASA's role.
54 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Martin |  | Mr. Martin. Sure, and I think Bill could go into a lot greater detail. Again, under the contracts, since this is a commercial spaceflight, the FAA gives the license, and under the contract, the contractor leads the accident investigation review, unlike a past Challenger accident or something like that where NASA itself would convene an independent accident investigation board. My sense is that NASA is a member, sort of an advisory member, of Orbital's, and soon to be SpaceX's, accident review boards, but they aren't leading that activity. And perhaps Bill could go deeper on that.
55 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412512 | Member | Bera | Ami | Mr. Bera. That would be great.
56 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. The NASA team is participating directly along with the FAA team and NTSB on the SpaceX accident board. They developed a fault tree, just as NASA has done, and the way they disposition each fault item is all three entities--NASA, FAA, and NTSB--and SpaceX all have to agree that this item is closed and not contributing to this accident. So it's by consensus. It's the engineering teams essentially led by SpaceX but fully represented by the government, and the government can say whether we accept or do not accept their explanation for what the root cause was. So it's a fairly effective way for us to have good insight in. We can do our own independent research on the side and contribute directly to the conclusions and make sure that we are representing the government. So we have the best from the FAA, and the best from NASA, participating in those activities along with the contractor-led activity.
57 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412512 | Member | Bera | Ami | Mr. Bera. And do you feel confident that there's that transparency in there and that we as a body, Congress, will be able to see that transparency and get the full details?
58 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. So far it's been extremely transparent. It was the same with the Orbital investigation. We had that same transparency with them, and it's been effective for both and we can show direct evidence of where that transparency is and how it's being implemented.
59 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412512 | Member | Bera | Ami | Mr. Bera. Okay. Great. And with that I'll yield back.
60 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you. Now I'd like to recognize the gentleman from Florida, Mr. Posey.
61 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412309 | Member | Posey | Bill | Mr. Posey. I thank you, Mr. Chairman. Mr. Gerstenmaier, we know that planning for the ISS began 20 years before it was actualized, and now we're less than ten years out from the administration's proposed extension to 2024. Does NASA have plans for some sort of station in low Earth orbit beyond 2024, perhaps some sort of public/private partnerships? Perhaps there are current international partners for an ISS replacement? Or does NASA intend to leave any LEO station entirely to commercial companies?
62 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. I think at this point we're looking to see if we can leave low-Earth orbit to commercial companies. What we're doing is we're allowing them to do investigations on Station to see if they can get a market return, and it makes sense to do that. Then we believe the agency's role is then to push further out into space to go into the region around the moon we call the proving ground region of space. We will move our research and our endeavors into that further region that helps the agency get prepared to take bigger missions ultimately towards Mars. So at this point, we're envisioning the low-Earth orbit to essentially be more of a private-sector activity, and we'll use the remaining lifetime of Station to let the private sector understand the benefits of microgravity research to their terrestrial investigations and see if it helps them from a fundamental research standpoint.
63 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412309 | Member | Posey | Bill | Mr. Posey. Now that's great to hear. Our government is investing in capitals, Orion, Dragon, CST-100, Cygnus. Most capitals are optimized to get crew and cargo back and forth to the ISS. What role will capitals play once the International Space Station reaches the end of its life?
64 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Again, for the Commercial Crew Program and also the Commercial Cargo Program, the companies have an interest just beyond the NASA need. They're building these capsules. They'll own the intellectual property. They'll be able to operate these capsules for their own purposes. If this private station we discussed earlier is available, they can use this transportation system to deliver cargo to it. They can deliver a crew to it, et cetera, outside of the government. So this will essentially allow the private sector to go get transportation services on its own from these companies that we've enabled through these initial start-up contracts on ISS.
65 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412309 | Member | Posey | Bill | Mr. Posey. That's great. The Space Shuttle and X-37, both examples of reusable spacecraft that lands on a runway also have had track records of success. Has NASA completely ruled out the use of reusable runway-capable vehicles for crew or cargo in the future?
66 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. The simple answer is no. I think in the case of the Orion vehicle, it's geared towards deep space activities where carrying wings makes it very difficult to reenter into the Earth's atmosphere. So the deep space vehicles will typically be a capsule-type vehicle, but for low-Earth orbit transportation, winged vehicles are very nice and have many advantages as we got to see through the Shuttle Program.
67 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412309 | Member | Posey | Bill | Mr. Posey. Thank you, Mr. Chairman. I yield back.
68 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, and I'd like to now recognize the gentleman from Virginia, Mr. Beyer.
69 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412657 | Member | Beyer | Donald | Mr. Beyer. Thank you, Mr. Chairman. Mr. Gerstenmaier, on the one hand we've had the three unfortunate losses that have been previously mentioned. On the other hand, it seems that our commercial space industry is getting ready to grow exponentially, adding great value to our economy and our civilization of the new satellites, internet, space tours of even Mars are talked about. Can you help us put these accidents in the proper perspective, especially compared to train and airline and automobile accidents, 30,000 deaths last year, by the way, NASA tragedies and all the transportation accidents in history? Are we looking at the relatively two or three that have come up in the right perspective compared to the last 150 years?
70 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. That's an interesting question. Again, I think the positive thing is that in all three of these cases, there's been no loss of life. So that says our basic processes and procedures are in place. So we protected the public. We protected the launch site. We did the right things. I think the important thing is to not get so fixated on the problem but how can we learn from this problem, right? As an emerging industry and developing new transportation system, the more we fly, there will be small problems. They're acceptable in this case. As we described earlier, the impacts are not devastating to Station. They hurt research, but they're still recoverable. The real tragedy will be if we don't learn from these events and we don't understand the engineering behind the failures and improve overall the industry. So I think just as the aviation industry has suffered a lot of failures throughout its history, the reason for its success today and the safety we get in the aircraft industry is a result of lessons learned and those lessons being applied to build better and safer aircraft. We need to do the same thing in the space industry. We need to take this learning from these events, internalize it, not be afraid of it, figure out how to make design changes, change the way we build spacecraft and build a more robust transportation system. So I see this as a painful but maybe somewhat necessary learning process. It's excellent to learn on cargo. We do not want to learn on crew. We will learn from cargo and apply those lessons to crew.
71 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412657 | Member | Beyer | Donald | Mr. Beyer. Well, thank you for your positive and your optimistic attitude which I very much appreciate. While you have the microphone though, the Aerospace Safety Advisory Panel, ASAP, has identified micro-meteoroid and orbital debris as a top safety risk facing ISS. How does NASA address these concerns about orbital debris?
72 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. We have shielding on board our Space Station and spacecraft that can protect for some debris. We cannot protect for all debris. We've recently implemented some changes to the Progress vehicle, the Progress launch that just occurred. It had new debris shields on that Progress vehicle. So we're continuing to improve the debris protection capability, and then we actively train on orbit. Just as we train terrestrially for fire drills, et cetera, we train for evacuation drills of Space Station in case we get hit by a piece of micro-meteoroid debris that penetrates a pressure shell. So we're prepared in that event. It is our highest risk when we look across the risk scenario. We protect it with the shielding levels that we can protect for it at this stage of Station's life.
73 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412657 | Member | Beyer | Donald | Mr. Beyer. All right. Thank you very much. Dr. Pawelczyk, you testified that during the 2000s, it resulted in NASA's priorities that the life, space life, and physical sciences were particularly hard hit, and a lot of scientists actually left the field. Do you have any concerns about the level of the workforce and expertise in that field today, especially as we get ready to think about man's missions to Mars?
74 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Pawelczyk |  | Dr. Pawelczyk. Thank you very much for the question. I'd say the short answer is no. You're absolutely right that those particular functions were very hard hit. We saw about an 80 percent decrement in the science portfolios in fundamental biology and in the physical sciences. One of the great things that has happened since 2011 is that NASA has reinstituted a ground-based program. If you look at the numbers of people who are applying, they're in the hundreds for solicitation right now. There's active funding that is happening and bringing research up to the Station. So you're starting to see that coming back. But what's even more interesting about it is that you're seeing maybe some of the youngest scientists that have really schooled in the entrepreneurial spirit saying, hey, this is something I'd like to take an opportunity and check out. You know, the ISS Research Conference this week was about three times bigger than what it was just a year ago. So there's a growing spirit, and we need to continue to feed that spirit, and I think great things will happen as a result.
75 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412657 | Member | Beyer | Donald | Mr. Beyer. That's great, and thank you for your enthusiasm. Mr. Chair, I yield back.
76 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Yes, sir. Thank you. Now I'd like to recognize the gentleman from Oklahoma, Mr. Bridenstine.
77 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412567 | Member | Bridenstine | Jim | Mr. Bridenstine. Thank you, Mr. Chairman, and thank you to all of our panelists for coming and testifying before this Committee. Mr. Gerstenmaier, I appreciate your long and distinguished service at NASA going back to negotiating with the Russians on the Mir program and other things in the '90s, and that's really where I'd like to start today. When you think about right now, given the recent accidents that we've gone through, we are seeing how important our reliance is on things like the Russian Progress cargo spacecraft and of course the Russian Soyuz crew spacecraft. Given how the relationship has changed between the United States and Russia, and we've even heard that, you know, the Russians have talked about pulling out of the International Space Station, what is your judgment on how this relation can go forward? How is it going on the civil space side given the strained relations in other areas? Can you share with us your opinion on that?
78 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Yes. On the civil space side, the relationship between the United States or between NASA and the Russians is very strong. We exchange data every day back and forth. We pass many commands to the Space Station, Russian commands through UAS. We use their assets as you've said for transportation reboost. We're very much mutually dependent upon each other for operations in space, and from a technical standpoint, the relationship is extremely strong, extremely transparent in spite of the governmental tensions between the two governments. So the challenge of human spaceflight kind of transcends a little bit of the toughness of the outside world, and we're working together extremely effectively with the Russians. The recent Progress loss, they've been sharing data with us. We've been working together to actively get ready to go fly crew on the 23rd of this month with the Russians, and they've been open with us, sharing data with us, helping us understand. They understand our needs. So the relationship is extremely strong between the civil space side.
79 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412567 | Member | Bridenstine | Jim | Mr. Bridenstine. How confident are you that they will continue the partnership beyond 2020?
80 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Again, I think they're working through their governmental approval process. I think it's likely potentially by the end of this year when their federal space program gets approved that there will be an extension of the Russians to support the Space Station through at least 2024.
81 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412567 | Member | Bridenstine | Jim | Mr. Bridenstine. Mr. Elbon, we have heard the IG has a report indicating that the operations of the ISS are going to become more difficult because of the ability to take replacement parts to the International Space Station. Recently Boeing had a report that might not have contradicted but dealt with some of those issues. Can you share with us the Boeing position? They were suggesting that beyond 2020, things get really difficult. I think your report suggested 2028. Can you share with us how you're dealing with those issues?
82 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Elbon |  | Mr. Elbon. Sure. Thanks for the question. The study that we did looked at things like the structural integrity of the elements on board, the ability to survive micro-meteorite kind of penetration and came to the conclusion that through 2028 is completely feasible relative to the hardware that's on orbit. The other part of the question is what about the logistics resupply to replace boxes that fail on orbit of computers, et cetera, and to supply the crew? And based on the logistics model that NASA's laid out and is using for the procurement of Commercial Resupply Services 2, you know, that kind of volume and up-mass is sufficient to support the logistics resupply that's necessary based on our analysis. So we think through 2028 is completely doable.
83 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412567 | Member | Bridenstine | Jim | Mr. Bridenstine. Thank you. Thank you for that testimony. Mr. Gerstenmaier, I appreciated Mr. Posey's question about, you know, what comes next after the ISS? Clearly whether it's 2020, 2028, we could lose partners. We don't know when we might lose certain partners. We have to think about what comes next in LEO. And I would like to just follow up with that. Can NASA provide a report to Congress on its plans for a roadmap or a timeline for certifying and testing, you know, a post-ISS station in LEO? And I understand this question was about commercial and things like that, and certainly, that's of interest as well. But it would have to be tested and certified, and NASA would have to be involved, is that correct? Can you provide a timeline to Congress for that?
84 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Again, I think the way we need to think about this is that the next private Space Station may not be--in fact, I don't believe it will be as massive or as big as this Space Station we have today, with this International Space Station. There's been discussion by the SpaceX Corporation of using their crew transportation modules called Dragon Lab where they can do individual investigations. We've talked to Orbital about potentially using their cargo vehicle as a temporary space station in low-Earth orbit. So I think when we think about the private sector taking over, we don't need to think about this big massive investment of a space station. They can learn what research really benefits them. If it's in the pharmaceutical area, if it's in materials processing, if it's in protein crystal growth, they can build a unique capability to do that. It can be much smaller. So I think the private sector has the capability and can do that on their own, and again, I think NASA's role is to kind of move that human presence further. And we want to go into the region around the moon so there may be a habitation capability again supplied potentially by the private sector for cargo in the vicinity of the moon. But I think NASA's next focus is some kind of habitation capability potentially in the vicinity of the moon.
85 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412567 | Member | Bridenstine | Jim | Mr. Bridenstine. Roger that. I yield back.
86 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you. And now I'd like to recognize the gentleman from Colorado, Mr. Perlmutter.
87 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412192 | Member | Perlmutter | Ed | Mr. Perlmutter. Thanks, Mr. Chairman, and thank you to the panelists. Mr. Administrator, it's good to see you. Some days you're here after we've had successes. Some days you're here after we've had some disappointments but appreciate the fact that we just keep moving forward. And it's not easy. You know, this is a risky business that you all are in, and we recognize that. And we don't want to have many disappointments. We want to have mostly successes. And I became more comfortable in understanding the kind of oversight that goes with the contractor-led investigation process, that in fact you are very involved and that there has to be some kind of sign-off as part of all of this because, oftentimes we have everybody looking over everybody else's shoulder. This seems to be a pretty sensible way to approach it, and I appreciate that. My questions are generally for you, Dr. Pawelczyk, and for you, Ms. Oakley, just really on what our research is doing on the Space Station that will help us as we move forward to sending our astronauts to Mars and for you so we have the researcher and the futurist, if you will, sitting next to the one who has to figure out how do you pay for it and what's the return. So I'd like to have you answer. Just generally, how do you see the Space Station advancing our goal of going to Mars? And I'd like to ask you, Ms. Oakley, what do you see in terms of the cost and the benefits from an accountant's point of view? So I'll just turn it over to you two.
88 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Pawelczyk |  | Dr. Pawelczyk. To make sure that Ms. Oakley has time, I'll be brief. There are really three issues that we're dealing with here. They are the biological changes that we see in this continuous reduced gravity environment. Bone and muscle are some of the largest. It is this very energetic radiation environment that we understand to a large extent from the standpoint of solid tumors, but when we start to look at interactions of things like effects in the brain, accelerated cardiovascular disease----
89 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412192 | Member | Perlmutter | Ed | Mr. Perlmutter. Is this part of why you have one Kelly on the Space Station and one Kelly on the ground?
90 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Pawelczyk |  | Dr. Pawelczyk. It is. It's an absolutely unique experiment because genetically they're identical. And so the changes in space give you a chance to really talk about what's the variation that's exclusively because of the space environment. And then of course there are the behavioral issues. You know, we're moving in that futuristic role. Right now the ISS really works in concert with the ground. When we begin to go to inter-planetary operations, those crew members are going to be working quite autonomously from the ground. It's just a matter of distance. And so how people function, independent of this planet, will be very different than how we operate on the ISS today.
91 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412192 | Member | Perlmutter | Ed | Mr. Perlmutter. Thank you.
92 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Oakley |  | Ms. Oakley. The bottom line is NASA does need a robust science program on the International Space Station to be able to achieve those longer-term exploration goals. However, NASA has to be able to pay for it, and the Congress has to be able to pay for it. And that relies on a robust commercial participation in low-Earth orbit to be able to do some of the things that NASA needs to divert funding for the longer term exploration goals, too. Like Mr. Gerstenmaier was referring to, being able to establish those markets in low-Earth orbit to do some of the research that's going to be required to support those long-duration human exploration flights is going to be essential, and getting them to pay for it is also going to be essential because going to Mars is expensive.
93 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412192 | Member | Perlmutter | Ed | Mr. Perlmutter. So are you comfortable with the accounting and the auditing that's gone on to date on this program? I mean, the numbers?
94 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Oakley |  | Ms. Oakley. On the International Space Station program? I haven't looked specifically at the accounting associated with that. What I will say is that I haven't seen any cost estimates associated with extending the International Space Station program beyond 2020, and I think that that's going to be key for the understanding of approving the funding and for everybody getting a very good understanding of what it's going to take to do the extension, to do the science that's required and to do it safely.
95 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412192 | Member | Perlmutter | Ed | Mr. Perlmutter. Okay. Thank you. Just one more question, and to Mr. Martin, we've had some incidents now where there have been some failures. We had some schools in Colorado that had experiments on both the Orbital launch and also most recently on the SpaceX, same school. They did it twice, and they lost both. How do we account for the cargo that's lost? Is there any compensation to those people or those schools or whatever?
96 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Martin |  | Mr. Martin. There is not. I think CASIS on the two flights of SpaceX and the Orbital failures lost over $650,000 of CASIS-funded experiments on those flights. The poor school children in your district lost two sets; NASA, as Mr. Gerstenmaier indicated, over $100 million, that's gone. The taxpayers are paying for that.
97 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412192 | Member | Perlmutter | Ed | Mr. Perlmutter. Okay. Well, I thank you for your testimony. Thank you all for being here today, and I yield back.
98 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you, sir. And now I'd like to recognize the gentleman from California, Mr. Knight.
99 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412614 | Member | Knight | Steve | Mr. Knight. Thank you, Mr. Chair. Just a couple of questions. Mr. Gerstenmaier, as a police officer who does investigations on accidents, we have seen a big change in our accident investigation over the last 50 years. I would expect to have seen a big change in investigations over space problems over the last 60 years. It hasn't been easy going to space in the 1960s. It isn't easy today. Can you give me an idea of how investigations go today and how we can either move through the process, making sure that we're going through and hitting the points and making sure that we're becoming safer as we move through the investigation, but also making sure we can go quicker because the faster we can move, the faster we can do more of this.
100 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Kind of our underpinning is first of all we need to be careful we don't jump to conclusions or assume that we know what the failure is to begin with. So we do a very methodical process of where we gather all the data. We need to make sure the time synchronization of that data is all critical, and that's not easy. You know, these events occur in milliseconds. So if you have a camera that's running and the time is on that, you have to make sure that the time on that camera is identical to the telemetry that's coming from the spacecraft. You know, is the timing of when the event occurred recorded on the spacecraft versus recorded after it's received on the ground? So that radio delay time to get down is important. So the first thing is to gather the data, get it all time synchronous. Then you can start through the methodical process of building what we call a fault tree. So we essentially brainstorm. There are now electronic tools available that automatically build a fault tree for us. They ask inquisitive questions. You lay out all the potential failures that could occur, that could have contributed to the event, which ones have to occur maybe with another event. Then your team meticulously goes through and then crosses off each one of those events as they move forward. In terms of speed, what we're seeing here in the case of SpaceX is because they're a very much vertically integrated company. They do almost all of their work in-house. They immediately went to testing certain components. So even though they showed up on the fault tree, they said why don't we just go ahead and build up a test rig right now and we'll be prepared to go test. So even these short number of days between the event and now they're off, actually off in the laboratory doing some stress tests on some components that may contribute kind of as a parallel activity to this more methodical process I laid out. So I think the advantage and the speed piece is we can use tools. We can use analysis. We have software, and then we can do physical tests in a much faster time than we did before.
101 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412614 | Member | Knight | Steve | Mr. Knight. No, and I agree. I talked to SpaceX several times since the incident, and Virgin and The Spaceship Company, after Spaceship II went down. And they were. They were jumping on it quickly, and they were learning things very fast. And it seems to me that the investigation process, and now with private companies being in fault, it seems like it is going a little bit faster. And that is a good thing. We want to make it safer. I know everyone wants to make it as safe as they possibly can, and that's the truth. Spaceflight still is in its infancy, and we're still learning and we will be for hundreds of years yet. And the faster we can get through some of these investigations, the faster we can move and progress. Doctor, I just had one question for you because I think that there was some good conversation there that we've got an astronaut working today, and we've got one on the ground. And I think that we'll get some good information there on what the effects are on the body when we actually send people to Mars on such a long, prolonged spaceflight. Can you give us an idea of what we're going to look at in the next 35 years, or maybe shorter as Administrator Bolden thinks, of when we are going to go to Mars and the effects on the body, not just the radiation but the time in space?
102 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Pawelczyk |  | Dr. Pawelczyk. So Mr. Knight, I apologize. I forgot my crystal ball this morning. But I'll do the best I can.
103 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412614 | Member | Knight | Steve | Mr. Knight. You're a kinesiologist. You should know this.
104 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Pawelczyk |  | Dr. Pawelczyk. So we have mentioned, you know, a couple of those risks that we're seeing in the radiation realm. What's been really interesting to look at, if I talked to you ten years ago I would have told you that I expected to see about 50 percent bone loss from a human being. We thought that that's essentially what gravity confers. We've seen with some of the implementation strategies for countermeasures on the ISS, that we're looking probably a lot better than that. I'm not willing to say that we have bone completely mitigated at this point. But some of the loading strategies are considerably better. We've also seen some newly-emergent risks, and that's always the problem. One particular with vision of astronauts. And that is actively being worked on by NASA. So there's been a number of ground-based research protocols. So this is a great example of how NASA quickly identified a problem, immediately engaged the scientific community to try to effect solutions.
105 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412614 | Member | Knight | Steve | Mr. Knight. Very good. Thank you, Mr. Chair. I yield back.
106 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Yes, sir. I'd like to recognize the gentleman from Ohio, Mr. Johnson. Mr. Johnson of Ohio. Well, thank you, folks, and I'm a big fan of space exploration. I'm a big Buck Rogers fan, Star Trek, all of those kinds of things, growing up with them as a kid. I say that jokingly, but I can tell you that sitting in my living room floor between the summer of my ninth- and tenth-grade year and watching Neil Armstrong and Buzz Aldrin land on the moon, it captivated me as it did the rest of the world, and I've never gotten over that. So I have tremendous respect for what you folks do and the discoveries that we're making through our space exploration process. Mr. Gerstenmaier, just one question for you to start off with. The ISS has not yet been extended by Congress. However, the administration has proposed to extend to 2024. How many of our international partners have agreed to extension? And what steps is NASA taking to build a coalition of our international partners for an extension?
107 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. The Canadian Space Agency has agreed to extend to 2024. So we have one partner on board, that's the Canadian Space Agency, who does a lot of our robotic activities and have the robotic equipment aboard Station. As I described earlier, the Russians, potentially by the end of this year, could be on board with the extension to 2024. The Japanese are also actively looking at Station extension. They could do that again probably by the end of this year, possibly by the start of their next fiscal year which is in April of 2016, and the Japanese are actively working on that and we're working with them. Mr. Johnson of Ohio. All right.
108 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. And the European Space Agency, they're again working through their overall budget process. They've committed to support us on the Orion capsule as you know. The teams in Ohio are working with them on the European Service Module that sits underneath the Orion capsule. They're pretty much committed. They're not committed to Station yet. They will do probably that in 2017 formally, but they're doing all the activities of getting with all the member states and all the member countries to approve, and they see again tremendous benefit. It's just working through their big governmental process on the ESA side. So I think all partners are heading towards Station extension to 2024 in a varying timeframe. Mr. Johnson of Ohio. A quick follow-up. How significant of a partner are the Russians? I mean, we're pretty dependent upon the Russians right now in terms of getting there and back, correct?
109 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Yes. We're dependent upon them for crew transportation. We also use them for altitude adjustments of Space Station. They provide the propellant that reboosts Station. They're dependent upon us for solar as ray or power generation. They also use us for commands and other activities. So we're kind of mutually dependent back and forth between both. Mr. Johnson of Ohio. Are you having any discussions--I'm sure you've heard the testimony of the potential incoming new Chairman of the Joint Chiefs who has stated that the Russians are our biggest security risk, security threat? I mean, we're kind of in a dichotomy with the Russians here. You guys concerned about that? And what's your back-up plan?
110 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Again, I would say, first of all, from a civil space standpoint, as I described earlier we have a very strong relationship with the Russians and will continue to do that. I think we need to again look at what happens if the Russians pull out in certain key areas. As we're working hard on the Commercial Crew Program, we want to end our sole reliance on the crew transportation system as soon as we can, and funding for that is absolutely critical to get it in place so we can have a U.S. capability to augment the Russians in the December 2017 or so timeframe. So I think we're moving out on crew transportation. The other areas that I described where we're dependent, we have work-arounds and we can put systems in place to recoup that if we have to. But at the end, I think it's advantageous to us if we can cooperate. There's real advantages to us. That's the right way to go forward. These endeavors require of us all to work together, but we also need to be not so naive that if a problem occurs, that we can't continue on without a certain partner. Mr. Johnson of Ohio. Okay. All right. Well, you know, I guess, you know, we've had some failures with the commercial avenue. And I'm sure that you are, but I hope there's a lot of discussion going on because if we continue to experience similar failures like we had with the Commercial Cargo Program and the Russians were to back out, our options become smaller and fewer. Okay, Mr. Chairman. I yield back.
111 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you. Now I'd like to recognize the gentleman from California, Mr. Rohrabacher.
112 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 400343 | Member | Rohrabacher | Dana | Mr. Rohrabacher. Thank you very much, Mr. Chairman. And I remember when the Space Station was first approved. It only won by one vote in this Committee, one vote. Boy, I'm glad I voted for it. Don't disappoint me. Don't disappoint me now. Does anyone here know the level of CO<INF>2</INF> that is in the atmosphere of the Space Station? You have an internal atmosphere. What element do we put CO<INF>2</INF> in? There's a lot of talk about CO<INF>2</INF> in the planet now. What does CO<INF>2</INF> do in the Space Station?
113 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. I believe we've been holding it low because of the potential eye problems. I think we're running about three millimeters of mercury of partial pressure of CO<INF>2</INF> on board Station.
114 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 400343 | Member | Rohrabacher | Dana | Mr. Rohrabacher. How does that compare to the CO<INF>2</INF> that we have in our atmosphere here?
115 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. It's higher than the atmosphere we have in the room here, and we've typically allowed, prior to the intracranial pressure problems associated with the vision, we allowed it to go up on the order of six or so millimeters per mercury, and that's dramatically higher than the environment here. So it's higher CO<INF>2</INF> levels on board Station than we see here.
116 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 400343 | Member | Rohrabacher | Dana | Mr. Rohrabacher. Have there been any health-related problems, this increased level of CO<INF>2</INF> that astronauts breathe in during their time at the Space Station as compared to what they would breathe in here?
117 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Yes, we're not sure but we think it could contribute to the intracranial pressure problem which causes the eye and vision problem we described. At higher elevated levels of CO<INF>2</INF> you can get headaches. You can have some other physiological problems. And again, we try to control that as low as we can. We have a Russian device that removes carbon dioxide. We have a U.S. device that removes carbon dioxide. Then we also have some absorbent material that also removes it. And then we have a next generation of system that will fly on the Orion capsule that's also on board Station, and we can use that also to remove CO<INF>2</INF>.
118 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 400343 | Member | Rohrabacher | Dana | Mr. Rohrabacher. Because we are actually exhaling CO<INF>2</INF> all the time, right? So we have to be--if you're in an enclosed environment, be very concerned with what the human body itself is exhaling. In terms of the future of Space Station, do we have plans to expand, put different elements onto the Space Station at this point?
119 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Currently on the U.S. side, we just reconfigured the permanent multi-purpose module from one location to another location. That was to make room for a docking adaptor that we discussed earlier to let commercial vehicles come. That's about all we're going to do on the U.S. side. There's no major new additions coming. The Russians have talked about a solar power platform to provide some solar energy for their segment. The Russians have also talked about a multi-purpose logistics module, another research module that they may add to Station.
120 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 400343 | Member | Rohrabacher | Dana | Mr. Rohrabacher. Does the----
121 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. So the Russians may add some additional modules, but we on the U.S. side don't have any major additions planned.
122 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 400343 | Member | Rohrabacher | Dana | Mr. Rohrabacher. The Bigelow Company has actually invested a considerable amount of money in developing a new concept for space habitat, the inflatables. Is there any use of this technology?
123 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | N/A |  | Gerstenmaier |  | Mr. Gerstenmaier. Yes, it'll be added to Space Station next year. It's a demonstration capability. This is an expandable module that will be added to the outside of Station. It will stay there for about a year or year-and-a-half, and then we'll remove it from Station. Its purpose is to investigate the advantages of an expandable module. So instead of a rigid pressure shell, it's to understand what we can gain from the expandable technology. It has some very thick walls, so it may be better from a micro-meteoroid to penetration standpoint. It also may be better thermally. That needs to be looked at. And the acoustic environment may be better. So the idea is to get it on orbit, actually take those claims, test them on orbit with Space Station, use the unique capabilities of Station, confirm if that module technology is something we want to use going forward.
124 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 400343 | Member | Rohrabacher | Dana | Mr. Rohrabacher. And it might also be cheaper than the traditional way of building a space station which is something we should be concerned about. Let me just note two things, one is that orbital debris continues to be and always was and is an expanding concern. I believe that this is something NASA should look at, not just in terms of Space Station, but we should be thinking about international cooperative effort to just deal with the debris problem. That's something we need to, this Committee should be dealing with at least in the time ahead. And second and last of all, let me just note that your report on your cooperation with Russia during this time period when there are, how do you say, frictions going on between the United States and Russia, I think demonstrates a very wonderful aspect of space and that is once you get up there, you look back down on the Earth and some of those problems don't seem as important or we're able to put it in perspective, and I'm happy to hear that we are and that the Russians are putting these areas of friction in perspective to the point that we can work together and create a better world while we're doing it. So thank you very much for demonstrating that to all of us.
125 | Space Subcommittee | HSSY-16 | CHRG-114hhrg97570.txt | THE INTERNATIONAL SPACE STATION: ADDRESSING OPERATIONAL CHALLENGES' | 412655 | Chair | Babin | Brian | Chairman Babin. Thank you. We have just had votes called, and I want to thank the witnesses for their valuable testimony and the members for all their questions. I'd really, if we would have had time, I would have liked to have gone through with a second round, but the record will remain open for two weeks for additional comments and for written questions from members. And it's our hope that the Office of Management and Budget will work more expeditiously with NASA to put together responses to these questions. The Committee is still waiting for NASA's responses to questions for the Commercial Crew hearing from six months ago. Mr. Gerstenmaier, please send back the message that these delays are not acceptable. The witnesses are excused, and this hearing is adjourned. Thank you.